## Cover
Kalindo Cove - Villa Development Underwriting & Cash Control
Model overview | Model overview
Field | Value
Model version | v3.1
Last updated | 2026-07-24
Actuals through | 2023-12-31
Forecast through | 2025-12-31
Reporting currency | USD
Workbook map |  |  |  |  | Formula / input legend
Tab | Purpose | Data type | Notes | Go to tab | Class | Font | Fill | Meaning | Action
Dashboard | Executive KPIs and charts | Output | Presentation view | Open Dashboard | Editable input | Blue | White | User-controlled assumption | Update deliberately
Unit P&L | Unit economics and margins | Output | Sales VAT excluded | Open Unit P&L | Formula | Black | White | Same-sheet calculation | Do not overwrite
Cash Flow | Monthly actual and forecast cash flow | Calculation | Single monthly time axis | Open Cash Flow | Linked formula | Green | White | Cross-sheet reference | Trace to source tab
Allocation | Budget / actual / EAC by villa | Calculation | Formula-driven | Open Allocation | Control warning | Red | Pale red/yellow | Exception or failed check | Investigate
Villas | Unit register and sales / physical drivers | Input + formulas | One row per villa | Open Villas
Sales Plan | Future gross receipt milestones | Input + formulas | Percentages must sum to 100% | Open Sales Plan
Budget | Development budget, EAC, and cash schedule | Input + formulas | Direct unit inputs on right | Open Budget | Use instructions
Inputs | Core assumptions, FX, and category mapping | Input | Blue-font cells | Open Inputs | 1. Refresh bank and transaction-ledger source rows.
Vendors | Vendor master and standard categories | Master data | Maintain vendor roles | Open Vendors | 2. Update FX, villa sales assumptions, budget inputs, and receipt milestones.
Outflows | Actual payment ledger | Source + formulas | Reconciles by reference | Open Outflows | 3. Review Budget EAC and Cash Flow funding requirements.
Inflows | Actual receipt ledger | Source + formulas | Reconciles by reference | Open Inflows | 4. Resolve any FAIL or WARNING on Checks before relying on outputs.
5. Record material scope, pricing, or timing changes in Change Log.
6. Use Dashboard and Unit P&L for management review.

## Dashboard
Kalindo Cove - Development Dashboard
Executive view of unit economics, cost control, and forecast liquidity.
← Back to Cover
← Back to Cover
Gross revenue | Gross revenue | Gross revenue |  | Development EAC | Development EAC | Development EAC | Profit / (loss) | Profit / (loss) | Profit / (loss) | Profit margin | Profit margin
12067713.0537 |  |  |  | 10250864.5744 |  |  | 1816848.4793 |  |  | 15.06%
Peak funding need | Peak funding need | Peak funding need |  | Cash received | Cash received | Cash received | Costs paid | Costs paid | Costs paid
499616.299 |  |  |  | 832531.8 |  |  | 788238.5499
Unit economics | Unit economics | Unit economics | Unit economics
Villa | Revenue USD | EAC Cost USD | Margin
Horizon Ridge Top | 3100000 | 3010574.412 | 2.885%
Horizon Ridge 3BDR | 2970502.0537 | 1925561.8737 | 35.18%
4BDR Canopy House | 2650000 | 2558116.9426 | 3.467%
Meadow 1 | 1350000 | 1072716.0867 | 20.54%
Meadow 2 | 0 | 40919.295 | 0%
Palm Valley/E1 | 0 | 109021.5511 | 0%
Palm Valley/E2 | 0 | 154728.2913 | 0%
Palm Valley/E3 | 0 | 206727.9904 | 0%
Kiri 3 | 1997211 | 1172498.1315 | 41.29%
Cost control by section | Cost control by section | Cost control by section | Cost control by section
Section | Budget USD | Actual USD | EAC USD
Hard Costs | 6661090.9033 | 0 | 6661090.9033
Soft Costs | 902126.2035 | 413418.1769 | 905309.2619
Project Management | 1033698.6533 | 330235.5998 | 1033934.2531
Contingency | 1192289.6073 | 0 | 1192289.6073
Land | 177120 | 0 | 177120
Income Tax | 280442.8263 | 0 | 280442.8263
Other Costs | 0 | 677.7223 | 677.7223
Liquidity trend | Liquidity trend | Liquidity trend
Month | Ending Cash USD | Actual / Forecast
2022-02-01 | -7489.0404 | Actual
2022-03-01 | -7489.0404 | Actual
2022-04-01 | -9985.9193 | Actual
2022-05-01 | -17540.581 | Actual
2022-06-01 | -49135.0382 | Actual
2022-07-01 | -49139.9854 | Actual
2022-08-01 | -49139.9854 | Actual
2022-09-01 | -50704.4899 | Actual
2022-10-01 | -57163.6618 | Actual
2022-11-01 | -73145.9774 | Actual
2022-12-01 | 132934.1132 | Actual
2023-01-01 | 68998.8058 | Actual
2023-02-01 | 246581.3601 | Actual
2023-03-01 | 106138.2952 | Actual
2023-04-01 | 72649.4985 | Actual
2023-05-01 | 34325.3869 | Actual
2023-06-01 | -70374.4525 | Actual
2023-07-01 | -169984.4324 | Actual
2023-08-01 | -219993.1676 | Actual
2023-09-01 | -251022.8211 | Actual
2023-10-01 | -286735.7804 | Actual
2023-11-01 | 72174.5425 | Actual
2023-12-01 | 44674.5425 | Actual
2024-01-01 | 2991211.7366 | Forecast
2024-02-01 | 2457192.3224 | Forecast
2024-03-01 | 1923172.9083 | Forecast
2024-04-01 | 1389153.4942 | Forecast
2024-05-01 | 855134.0801 | Forecast
2024-06-01 | 321114.666 | Forecast
2024-07-01 | 1983503.1181 | Forecast
2024-08-01 | 1486879.2347 | Forecast
2024-09-01 | 990255.3513 | Forecast
2024-10-01 | 493631.4678 | Forecast
2024-11-01 | -2992.4156 | Forecast
2024-12-01 | -499616.299 | Forecast
2025-01-01 | 2175730.3929 | Forecast
2025-02-01 | 1710771.7634 | Forecast
2025-03-01 | 1245813.1339 | Forecast
2025-04-01 | 780854.5043 | Forecast
2025-05-01 | 315895.8748 | Forecast
2025-06-01 | -149062.7548 | Forecast
2025-07-01 | 1530407.6179 | Forecast
2025-08-01 | 1496898.1582 | Forecast
2025-09-01 | 1463388.6985 | Forecast
2025-10-01 | 1463388.6985 | Forecast
2025-11-01 | 1463388.6985 | Forecast
2025-12-01 | 1005825.8722 | Forecast

## Unit P&L
Kalindo Cove - Unit Economics
Forecast-at-completion P&L by villa. Sales VAT is excluded; income tax is included as a project cost.
← Back to Cover
Section | Line Item | Units | Horizon Ridge Top | Horizon Ridge 3BDR | 4BDR Canopy House | Meadow 1 | Meadow 2 | Palm Valley/E1 | Palm Valley/E2 | Palm Valley/E3 | Kiri 3 | Total
Revenue | Net sale price | USD | 2800000 | 2970502.0537 | 2650000 | 800000 | 0 | 0 | 0 | 0 | 1997211 | 11217713.0537
Revenue | Delayed income | USD | 300000 | 0 | 0 | 550000 | 0 | 0 | 0 | 0 | 0 | 850000
Revenue | Total revenue | USD | 3100000 | 2970502.0537 | 2650000 | 1350000 | 0 | 0 | 0 | 0 | 1997211 | 12067713.0537
Costs | Hard Costs | USD | 1979436.6452 | 1315569.4064 | 1802673.8282 | 791520.2081 | 0 | 0 | 0 | 0 | 771890.8153 | 6661090.9033
Costs | Soft Costs | USD | 134727.1419 | 76187.5437 | 96660.3327 | 36856.6361 | 40919.295 | 109021.5511 | 154728.2913 | 206727.9904 | 49480.4797 | 905309.2619
Costs | Project Management | USD | 351500.0786 | 199391.6216 | 255740.701 | 94603.9384 | 0 | 0 | 0 | 0 | 132697.9135 | 1033934.2531
Costs | Contingency | USD | 405335.1453 | 229930.0536 | 294909.4481 | 109093.2932 | 0 | 0 | 0 | 0 | 153021.6672 | 1192289.6073
Costs | Land | USD | 69345 | 30090 | 41715 | 20580 | 0 | 0 | 0 | 0 | 15390 | 177120
Costs | Income Tax | USD | 70000 | 74262.5513 | 66250 | 20000 | 0 | 0 | 0 | 0 | 49930.275 | 280442.8263
Costs | Other Costs | USD | 230.401 | 130.697 | 167.6327 | 62.0109 | 0 | 0 | 0 | 0 | 86.9807 | 677.7223
Costs | Total development cost | USD | 3010574.412 | 1925561.8737 | 2558116.9426 | 1072716.0867 | 40919.295 | 109021.5511 | 154728.2913 | 206727.9904 | 1172498.1315 | 10250864.5744
Returns | Profit / (loss) | USD | 89425.588 | 1044940.18 | 91883.0574 | 277283.9133 | -40919.295 | -109021.5511 | -154728.2913 | -206727.9904 | 824712.8685 | 1816848.4793
Returns | Profit margin | % | 2.885% | 35.18% | 3.467% | 20.54% | 0% | 0% | 0% | 0% | 41.29% | 15.06%
Returns | Profit on cost | % | 2.97% | 54.27% | 3.592% | 25.85% | -100% | -100% | -100% | -100% | 70.34% | 17.72%
Returns | Revenue per buildup m² | USD / m² | 1842.7153 | 3112.755 | 2165.0504 | 2981.5805 | 0 | 0 | 0 | 0 | 3144.7189 | 1104.1353
Returns | Cost per buildup m² | USD / m² | 1789.5586 | 2017.7742 | 2089.9819 | 2369.1773 | 76.3078 | 84.3233 | 86.4259 | 87.5354 | 1846.163 | 937.9028
Cash | Gross cash budget | USD | 3108000 | 3297257.2796 | 2941500 | 888000 | 0 | 0 | 0 | 0 | 2216904.21 | 12451661.4896
Cash | Actual cash received | USD | 443990 | 0 | 0 | 388541.8 | 0 | 0 | 0 | 0 | 0 | 832531.8
Cash | Remaining receipts | USD | 2664010 | 3297257.2796 | 2941500 | 499458.2 | 0 | 0 | 0 | 0 | 2216904.21 | 11619129.6896

## Cash Flow
Kalindo Cove - Monthly Cash Flow
Actual transaction-ledger cash through Dec 2023 and formula-driven forecast thereafter. USD reporting.
← Back to Cover
Line | Budget / Gross | Actual to Date | Remaining | Schedule Start | Schedule End | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Actual | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast | Forecast
 | time axis 2022-02-01 to 2025-12-01
Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows | Cash inflows
Horizon Ridge Top | 3108000 | 443990 | 2664010 | 2024-01-01 | 2025-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221995 | 0 | 221995 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 799203 | 0 | 0 | 0 | 0 | 0 | 532802 | 0 | 0 | 0 | 0 | 0 | 799203 | 0 | 0 | 0 | 0 | 0 | 532802 | 0 | 0 | 0 | 0 | 0
Horizon Ridge 3BDR | 3297257.2796 | 0 | 3297257.2796 | 2024-01-01 | 2025-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 989177.1839 | 0 | 0 | 0 | 0 | 0 | 659451.4559 | 0 | 0 | 0 | 0 | 0 | 989177.1839 | 0 | 0 | 0 | 0 | 0 | 659451.4559 | 0 | 0 | 0 | 0 | 0
4BDR Canopy House | 2941500 | 0 | 2941500 | 2024-01-01 | 2025-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 882450 | 0 | 0 | 0 | 0 | 0 | 588300 | 0 | 0 | 0 | 0 | 0 | 882450 | 0 | 0 | 0 | 0 | 0 | 588300 | 0 | 0 | 0 | 0 | 0
Meadow 1 | 888000 | 388541.8 | 499458.2 | 2024-01-01 | 2025-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 388541.8 | 0 | 149837.46 | 0 | 0 | 0 | 0 | 0 | 99891.64 | 0 | 0 | 0 | 0 | 0 | 149837.46 | 0 | 0 | 0 | 0 | 0 | 99891.64 | 0 | 0 | 0 | 0 | 0
Kiri 3 | 2216904.21 | 0 | 2216904.21 | 2024-01-01 | 2025-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 665071.263 | 0 | 0 | 0 | 0 | 0 | 443380.842 | 0 | 0 | 0 | 0 | 0 | 665071.263 | 0 | 0 | 0 | 0 | 0 | 443380.842 | 0 | 0 | 0 | 0 | 0
Other income |  | 381.2924 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1.9084 | 20.1 | 29.06 | 46.67 | 44.35 | 45.68 | 42.3357 | 35.4979 | 31.6478 | 28.89 | 29.243 | 25.9096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total cash inflows | 12451661.4896 | 832913.0924 | 11619129.6896 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 221996.9084 | 20.1 | 222024.06 | 46.67 | 44.35 | 45.68 | 42.3357 | 35.4979 | 31.6478 | 28.89 | 29.243 | 388567.7096 | 0 | 3485738.9069 | 0 | 0 | 0 | 0 | 0 | 2323825.9379 | 0 | 0 | 0 | 0 | 0 | 3485738.9069 | 0 | 0 | 0 | 0 | 0 | 2323825.9379 | 0 | 0 | 0 | 0 | 0
Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows | Cash outflows
Preliminaries | 406514.4849 | 0 | 406514.4849 | 2024-01-01 | 2025-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 21395.4992 | 21395.4992 | 21395.4992 | 21395.4992 | 21395.4992 | 21395.4992 | 21395.4992 | 21395.4992 | 21395.4992 | 21395.4992 | 21395.4992 | 21395.4992 | 21395.4992 | 21395.4992 | 21395.4992 | 21395.4992 | 21395.4992 | 21395.4992 | 21395.4992 | 0 | 0 | 0 | 0 | 0
Structure & Architecture | 3967507.1502 | 0 | 3967507.1502 | 2024-02-01 | 2025-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 220417.0639 | 220417.0639 | 220417.0639 | 220417.0639 | 220417.0639 | 220417.0639 | 220417.0639 | 220417.0639 | 220417.0639 | 220417.0639 | 220417.0639 | 220417.0639 | 220417.0639 | 220417.0639 | 220417.0639 | 220417.0639 | 220417.0639 | 220417.0639 | 0 | 0 | 0 | 0 | 0
MEP | 838926.4015 | 0 | 838926.4015 | 2024-02-01 | 2025-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 46607.0223 | 46607.0223 | 46607.0223 | 46607.0223 | 46607.0223 | 46607.0223 | 46607.0223 | 46607.0223 | 46607.0223 | 46607.0223 | 46607.0223 | 46607.0223 | 46607.0223 | 46607.0223 | 46607.0223 | 46607.0223 | 46607.0223 | 46607.0223 | 0 | 0 | 0 | 0 | 0
Provisional Sum | 125800 | 0 | 125800 | 2024-02-01 | 2025-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6988.8889 | 6988.8889 | 6988.8889 | 6988.8889 | 6988.8889 | 6988.8889 | 6988.8889 | 6988.8889 | 6988.8889 | 6988.8889 | 6988.8889 | 6988.8889 | 6988.8889 | 6988.8889 | 6988.8889 | 6988.8889 | 6988.8889 | 6988.8889 | 0 | 0 | 0 | 0 | 0
Landscaping | 175000 | 0 | 175000 | 2024-08-01 | 2025-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 14583.3333 | 14583.3333 | 14583.3333 | 14583.3333 | 14583.3333 | 14583.3333 | 14583.3333 | 14583.3333 | 14583.3333 | 14583.3333 | 14583.3333 | 14583.3333 | 0 | 0 | 0 | 0 | 0
Network & Infrastructure upgrade | 447700 | 0 | 447700 | 2024-01-01 | 2024-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 74616.6667 | 74616.6667 | 74616.6667 | 74616.6667 | 74616.6667 | 74616.6667 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
New Infrastructure | 139829.5333 | 0 | 139829.5333 | 2024-01-01 | 2024-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 23304.9222 | 23304.9222 | 23304.9222 | 23304.9222 | 23304.9222 | 23304.9222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Architect Cost | 293605.0464 | 223272.0577 | 70332.9887 | 2024-01-01 | 2024-12-01 | 7489.0404 | 0 | 2496.8789 | 7554.6617 | 31594.4572 | 0 | 0 | 0 | 5494.0452 | 9004.4926 | 12526.0371 | 29417.9876 | 0 | 44437.5688 | 0 | 0 | 62606.9353 | 10649.953 | 0 | 0 | 0 | 0 | 0 | 5861.0824 | 5861.0824 | 5861.0824 | 5861.0824 | 5861.0824 | 5861.0824 | 5861.0824 | 5861.0824 | 5861.0824 | 5861.0824 | 5861.0824 | 5861.0824 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Interior Designer | 180754.6185 | 49447.2826 | 131307.3358 | 2024-01-01 | 2024-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24616.5526 | 0 | 7291.76 | 14353.11 | 0 | 0 | 0 | 3185.86 | 0 | 0 | 10942.278 | 10942.278 | 10942.278 | 10942.278 | 10942.278 | 10942.278 | 10942.278 | 10942.278 | 10942.278 | 10942.278 | 10942.278 | 10942.278 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Landscape Designer | 30412.4403 | 0 | 30412.4403 | 2024-01-01 | 2024-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2534.37 | 2534.37 | 2534.37 | 2534.37 | 2534.37 | 2534.37 | 2534.37 | 2534.37 | 2534.37 | 2534.37 | 2534.37 | 2534.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Structure Engineer | 33733.3333 | 14999.2659 | 18734.0675 | 2024-01-01 | 2024-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4270.1913 | 3089.4412 | 0 | 4399.6334 | 0 | 3240 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1561.1723 | 1561.1723 | 1561.1723 | 1561.1723 | 1561.1723 | 1561.1723 | 1561.1723 | 1561.1723 | 1561.1723 | 1561.1723 | 1561.1723 | 1561.1723 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MEP Consultant | 11322 | 7826.58 | 3495.42 | 2024-01-01 | 2024-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2777.2767 | 0 | 0 | 0 | 0 | 0 | 5049.3033 | 0 | 0 | 291.285 | 291.285 | 291.285 | 291.285 | 291.285 | 291.285 | 291.285 | 291.285 | 291.285 | 291.285 | 291.285 | 291.285 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Quantity Surveyor | 97063.358 | 14851.6977 | 82211.6603 | 2024-01-01 | 2025-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12701.311 | 0 | 0 | 0 | 2150.3867 | 0 | 4326.9295 | 4326.9295 | 4326.9295 | 4326.9295 | 4326.9295 | 4326.9295 | 4326.9295 | 4326.9295 | 4326.9295 | 4326.9295 | 4326.9295 | 4326.9295 | 4326.9295 | 4326.9295 | 4326.9295 | 4326.9295 | 4326.9295 | 4326.9295 | 4326.9295 | 0 | 0 | 0 | 0 | 0
Notary | 124792.4167 | 29504.0626 | 95288.354 | 2024-01-01 | 2024-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6974.1238 | 196.4122 | 0 | 0 | 0 | 0 | 0 | 22333.5267 | 0 | 0 | 0 | 0 | 7940.6962 | 7940.6962 | 7940.6962 | 7940.6962 | 7940.6962 | 7940.6962 | 7940.6962 | 7940.6962 | 7940.6962 | 7940.6962 | 7940.6962 | 7940.6962 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Tax & legal advice | 17941.97 | 18417.3967 | 0 | 2024-01-01 | 2024-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1564.5045 | 965.1268 | 0 | 0 | 0 | 0 | 0 | 0 | 3561.8917 | 0 | 8780.1103 | 0 | 3545.7635 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Other professional fees | 40000 | 40000 | 0 | 2024-01-01 | 2024-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Land Survey | 11237.98 | 273.3333 | 10964.6467 | 2024-01-01 | 2024-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 273.3333 | 0 | 0 | 0 | 0 | 0 | 0 | 1827.4411 | 1827.4411 | 1827.4411 | 1827.4411 | 1827.4411 | 1827.4411 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Soil Test | 30850.6 | 12118.8687 | 18731.7313 | 2024-01-01 | 2024-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12118.8687 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3121.9552 | 3121.9552 | 3121.9552 | 3121.9552 | 3121.9552 | 3121.9552 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MEP Engineering | 30412.4403 | 0 | 30412.4403 | 2024-01-01 | 2024-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2534.37 | 2534.37 | 2534.37 | 2534.37 | 2534.37 | 2534.37 | 2534.37 | 2534.37 | 2534.37 | 2534.37 | 2534.37 | 2534.37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sitegrid / Other QS | 0 | 2707.6317 | 0 | 2024-01-01 | 2024-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2707.6317 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Staff | 126198.6533 | 0 | 126198.6533 | 2024-01-01 | 2025-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6009.4597 | 6009.4597 | 6009.4597 | 6009.4597 | 6009.4597 | 6009.4597 | 6009.4597 | 6009.4597 | 6009.4597 | 6009.4597 | 6009.4597 | 6009.4597 | 6009.4597 | 6009.4597 | 6009.4597 | 6009.4597 | 6009.4597 | 6009.4597 | 6009.4597 | 6009.4597 | 6009.4597 | 0 | 0 | 0
A&G Allocation | 907500 | 330000 | 577500 | 2024-01-01 | 2025-09-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 27500 | 0 | 0 | 0
Project Management | 0 | 235.5998 | 0 | 2024-01-01 | 2025-09-01 | 0 | 0 | 0 | 0 | 0 | 4.9472 | 0 | 0 | 0 | 0 | 0 | 15.5551 | 0 | 21.5708 | 0 | 0 | 0 | 0 | 193.5267 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Contingency | 1192289.6073 | 0 | 1192289.6073 | 2024-02-01 | 2025-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66238.3115 | 66238.3115 | 66238.3115 | 66238.3115 | 66238.3115 | 66238.3115 | 66238.3115 | 66238.3115 | 66238.3115 | 66238.3115 | 66238.3115 | 66238.3115 | 66238.3115 | 66238.3115 | 66238.3115 | 66238.3115 | 66238.3115 | 66238.3115 | 0 | 0 | 0 | 0 | 0
Interior Cost | 559813.3333 | 0 | 559813.3333 | 2024-08-01 | 2025-06-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50892.1212 | 50892.1212 | 50892.1212 | 50892.1212 | 50892.1212 | 50892.1212 | 50892.1212 | 50892.1212 | 50892.1212 | 50892.1212 | 50892.1212 | 0 | 0 | 0 | 0 | 0 | 0
Land Costs | 177120 | 0 | 177120 | 2025-12-01 | 2025-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 177120
Income tax | 280442.8263 | 0 | 280442.8263 | 2025-12-01 | 2025-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 280442.8263
Sales VAT | 1233948.4359 | 43907.0509 | 1190041.385 | 2024-01-01 | 2025-07-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 43907.0509 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 345433.5854 | 0 | 0 | 0 | 0 | 0 | 230289.0569 | 0 | 0 | 0 | 0 | 0 | 345433.5854 | 0 | 0 | 0 | 0 | 0 | 230289.0569 | 0 | 0 | 0 | 0 | 0
Bank fees | 0 | 0 | 0 | 2024-01-01 | 2025-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Withholding tax | 0 | 48.9123 | 0 | 2024-01-01 | 2025-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.023677 | 4.02 | 5.81 | 0 | 8.87 | 9.14 | 1.7965 | 7.1036 | 6.3296 | 5.78 | 0.038983 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Miscellaneous | 0 | 628.81 | 0 | 2024-01-01 | 2025-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 301.3159 | 43.7209 | 220.7815 | 6.9918 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Unmapped | 0 | 0 | 0 | 2024-01-01 | 2025-12-01 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Total cash outflows | 11480716.6297 | 788238.5499 | 10696574.4604 |  |  | 7489.0404 | 0 | 2496.8789 | 7554.6617 | 31594.4572 | 4.9472 | 0 | 1564.5045 | 6459.1719 | 15982.3156 | 15916.8178 | 63955.4073 | 44441.5058 | 140489.7349 | 33533.1467 | 38369.7917 | 104742.1751 | 99645.4779 | 50040.3829 | 31058.5435 | 35742.2023 | 29657.3867 | 27500 | 539201.7129 | 534019.4141 | 534019.4141 | 534019.4141 | 534019.4141 | 534019.4141 | 661437.4858 | 496623.8834 | 496623.8834 | 496623.8834 | 496623.8834 | 496623.8834 | 810392.2149 | 464958.6295 | 464958.6295 | 464958.6295 | 464958.6295 | 464958.6295 | 644355.5652 | 33509.4597 | 33509.4597 | 0 | 0 | 457562.8263
Net cash flow | [5 empty] | -7489.0404 | 0 | -2496.8789 | -7554.6617 | -31594.4572 | -4.9472 | 0 | -1564.5045 | -6459.1719 | -15982.3156 | 206080.0905 | -63935.3073 | 177582.5542 | -140443.0649 | -33488.7967 | -38324.1117 | -104699.8394 | -99609.9799 | -50008.7351 | -31029.6535 | -35712.9593 | 358910.323 | -27500 | 2946537.194 | -534019.4141 | -534019.4141 | -534019.4141 | -534019.4141 | -534019.4141 | 1662388.4521 | -496623.8834 | -496623.8834 | -496623.8834 | -496623.8834 | -496623.8834 | 2675346.692 | -464958.6295 | -464958.6295 | -464958.6295 | -464958.6295 | -464958.6295 | 1679470.3727 | -33509.4597 | -33509.4597 | 0 | 0 | -457562.8263
Beginning cash | [5 empty] | 0 | -7489.0404 | -7489.0404 | -9985.9193 | -17540.581 | -49135.0382 | -49139.9854 | -49139.9854 | -50704.4899 | -57163.6618 | -73145.9774 | 132934.1132 | 68998.8058 | 246581.3601 | 106138.2952 | 72649.4985 | 34325.3869 | -70374.4525 | -169984.4324 | -219993.1676 | -251022.8211 | -286735.7804 | 72174.5425 | 44674.5425 | 2991211.7366 | 2457192.3224 | 1923172.9083 | 1389153.4942 | 855134.0801 | 321114.666 | 1983503.1181 | 1486879.2347 | 990255.3513 | 493631.4678 | -2992.4156 | -499616.299 | 2175730.3929 | 1710771.7634 | 1245813.1339 | 780854.5043 | 315895.8748 | -149062.7548 | 1530407.6179 | 1496898.1582 | 1463388.6985 | 1463388.6985 | 1463388.6985
Ending cash | [5 empty] | -7489.0404 | -7489.0404 | -9985.9193 | -17540.581 | -49135.0382 | -49139.9854 | -49139.9854 | -50704.4899 | -57163.6618 | -73145.9774 | 132934.1132 | 68998.8058 | 246581.3601 | 106138.2952 | 72649.4985 | 34325.3869 | -70374.4525 | -169984.4324 | -219993.1676 | -251022.8211 | -286735.7804 | 72174.5425 | 44674.5425 | 2991211.7366 | 2457192.3224 | 1923172.9083 | 1389153.4942 | 855134.0801 | 321114.666 | 1983503.1181 | 1486879.2347 | 990255.3513 | 493631.4678 | -2992.4156 | -499616.299 | 2175730.3929 | 1710771.7634 | 1245813.1339 | 780854.5043 | 315895.8748 | -149062.7548 | 1530407.6179 | 1496898.1582 | 1463388.6985 | 1463388.6985 | 1463388.6985 | 1005825.8722
Funding required | [5 empty] | 7489.0404 | 7489.0404 | 9985.9193 | 17540.581 | 49135.0382 | 49139.9854 | 49139.9854 | 50704.4899 | 57163.6618 | 73145.9774 | 0 | 0 | 0 | 0 | 0 | 0 | 70374.4525 | 169984.4324 | 219993.1676 | 251022.8211 | 286735.7804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2992.4156 | 499616.299 | 0 | 0 | 0 | 0 | 0 | 149062.7548 | 0 | 0 | 0 | 0 | 0 | 0
Formulas:
Schedule Start = MINIFS('Sales Plan'!$C7:C42,'Sales Plan'!$A7:A42,[Line])
Schedule End = MAXIFS('Sales Plan'!$C7:C42,'Sales Plan'!$A7:A42,[Line])

## Allocation
Kalindo Cove - Cost Allocation
Budget, actual, and EAC allocated to villas using direct estimates or formula-driven physical/revenue drivers.
← Back to Cover
Budget ID | Section | Category | Horizon Ridge Top | Horizon Ridge 3BDR | 4BDR Canopy House | Meadow 1 | Meadow 2 | Palm Valley/E1 | Palm Valley/E2 | Palm Valley/E3 | Kiri 3 | Total USD | Check
Budget allocation | Budget allocation | Budget allocation | Budget allocation | Budget allocation | Budget allocation | Budget allocation | Budget allocation | Budget allocation | Budget allocation | Budget allocation | Budget allocation | Budget allocation | Budget allocation
HC01 | Hard Costs | Preliminaries | 128399.4728 | 81336.5868 | 115186.5002 | 41970.7251 | 0 | 0 | 0 | 0 | 39621.2 | 406514.4849 | 0
HC02 | Hard Costs | Structure & Architecture | 1173228.4947 | 774648.8294 | 1160416.3677 | 458986.3067 | 0 | 0 | 0 | 0 | 400227.1517 | 3967507.1502 | 0
HC03 | Hard Costs | MEP | 275221.984 | 181045.7299 | 180233.8656 | 98776.8182 | 0 | 0 | 0 | 0 | 103648.0038 | 838926.4015 | 0
HC04 | Hard Costs | Provisional Sum | 25160 | 25160 | 25160 | 25160 | 0 | 0 | 0 | 0 | 25160 | 125800 | 0
HC05 | Hard Costs | Landscaping | 35000 | 35000 | 35000 | 35000 | 0 | 0 | 0 | 0 | 35000 | 175000 | 0
HC06 | Hard Costs | Network & Infrastructure upgrade | 152201.7331 | 86337.8196 | 110737.3235 | 40964.0972 | 0 | 0 | 0 | 0 | 57459.0267 | 447700 | 0
HC07 | Hard Costs | New Infrastructure | 47536.9607 | 26965.774 | 34586.4379 | 12794.2609 | 0 | 0 | 0 | 0 | 17946.0998 | 139829.5333 | 0
SC01 | Soft Costs | Architect Cost | 45192.2831 | 25635.7343 | 32880.5222 | 12163.2063 | 14405.2249 | 34731.6785 | 48093.5293 | 63441.9279 | 17060.9398 | 293605.0464 | 0
SC02 | Soft Costs | Interior Designer | 27822.1168 | 15782.3492 | 20242.5208 | 7488.1401 | 8868.4134 | 21382.1642 | 29608.2361 | 39057.3037 | 10503.3742 | 180754.6185 | 0
SC03 | Soft Costs | Landscape Designer | 4681.1444 | 2655.4218 | 3405.8574 | 1259.8993 | 1492.1339 | 3597.6054 | 4981.6637 | 6571.4942 | 1767.2204 | 30412.4403 | 0
SC04 | Soft Costs | Structure Engineer | 5192.303 | 2945.3811 | 3777.7607 | 1397.4743 | 1655.0678 | 3990.4467 | 5525.6375 | 7289.0699 | 1960.1924 | 33733.3333 | 0
SC05 | Soft Costs | MEP Consultant | 1742.7052 | 988.5654 | 1267.9389 | 469.0377 | 555.4944 | 1339.3232 | 1854.583 | 2446.4481 | 657.9041 | 11322 | 0
SC06 | Soft Costs | Quantity Surveyor | 14940.1885 | 8474.9581 | 10870.024 | 4021.0537 | 4762.2462 | 11482.0007 | 15899.3162 | 20973.3676 | 5640.2031 | 97063.358 | 0
SC07 | Soft Costs | Notary | 14059.1042 | 6100.4895 | 8457.3586 | 4172.4186 | 4281.8989 | 18073.3845 | 27841.4664 | 38686.1053 | 3120.1906 | 124792.4167 | 0
SC08 | Soft Costs | Tax & legal advice | 4478.4098 | 4751.1162 | 4238.495 | 1279.5457 | 0 | 0 | 0 | 0 | 3194.4033 | 17941.97 | 0
SC09 | Soft Costs | Other professional fees | 6156.881 | 3492.5468 | 4479.5582 | 1657.0841 | 1962.531 | 4731.755 | 6552.1393 | 8643.1659 | 2324.3388 | 40000 | 0
SC10 | Soft Costs | Land Survey | 1266.07 | 549.3698 | 761.6138 | 375.7404 | 385.5995 | 1627.5695 | 2507.2184 | 3483.8149 | 280.9837 | 11237.98 | 0
SC11 | Soft Costs | Soil Test | 3475.6263 | 1508.1346 | 2090.7888 | 1031.4859 | 1058.5511 | 4468.0179 | 6882.8377 | 9563.7988 | 771.359 | 30850.6 | 0
SC12 | Soft Costs | MEP Engineering | 4681.1444 | 2655.4218 | 3405.8574 | 1259.8993 | 1492.1339 | 3597.6054 | 4981.6637 | 6571.4942 | 1767.2204 | 30412.4403 | 0
SC13 | Soft Costs | Sitegrid / Other QS | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PM01 | Project Management | Staff | 42902.9568 | 24337.0931 | 31214.8785 | 11547.0491 | 0 | 0 | 0 | 0 | 16196.6759 | 126198.6533 | 0
PM02 | Project Management | A&G Allocation | 308517.0265 | 175009.0937 | 224467.5475 | 83035.3321 | 0 | 0 | 0 | 0 | 116471.0001 | 907500 | 0
PM03 | Project Management | Project Management | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PM04 | Contingency | Contingency | 405335.1453 | 229930.0536 | 294909.4481 | 109093.2932 | 0 | 0 | 0 | 0 | 153021.6672 | 1192289.6073 | 0
HC08 | Hard Costs | Interior Cost | 142688 | 105074.6667 | 141353.3333 | 77868 | 0 | 0 | 0 | 0 | 92829.3333 | 559813.3333 | 0
LC01 | Land | Land Costs | 69345 | 30090 | 41715 | 20580 | 0 | 0 | 0 | 0 | 15390 | 177120 | 0
TX01 | Income Tax | Income tax | 70000 | 74262.5513 | 66250 | 20000 | 0 | 0 | 0 | 0 | 49930.275 | 280442.8263 | 0
TX02 | Sales Tax | Sales VAT | 308000 | 326755.2259 | 291500 | 88000 | 0 | 0 | 0 | 0 | 219693.21 | 1233948.4359 | 0
OC01 | Other Costs | Bank fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OC02 | Other Costs | Withholding tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OC03 | Other Costs | Miscellaneous | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OC04 | Other Costs | Unmapped | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  | 3317224.7503 | 2251492.9125 | 2848608.9983 | 1160350.8677 | 40919.295 | 109021.5511 | 154728.2913 | 206727.9904 | 1391641.9732 | 11480716.6297 | 0
Actual allocation through cut-off | Actual allocation through cut-off | Actual allocation through cut-off | Actual allocation through cut-off | Actual allocation through cut-off | Actual allocation through cut-off | Actual allocation through cut-off | Actual allocation through cut-off | Actual allocation through cut-off | Actual allocation through cut-off | Actual allocation through cut-off | Actual allocation through cut-off | Actual allocation through cut-off | Actual allocation through cut-off
HC01 | Hard Costs | Preliminaries | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HC02 | Hard Costs | Structure & Architecture | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HC03 | Hard Costs | MEP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HC04 | Hard Costs | Provisional Sum | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HC05 | Hard Costs | Landscaping | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HC06 | Hard Costs | Network & Infrastructure upgrade | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HC07 | Hard Costs | New Infrastructure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SC01 | Soft Costs | Architect Cost | 34366.4871 | 19494.7029 | 25004.0044 | 9249.5144 | 10954.4582 | 26411.7168 | 36572.7408 | 48244.4357 | 12973.9975 | 223272.0577 | 0
SC02 | Soft Costs | Interior Designer | 7611.0258 | 4317.4237 | 5537.5495 | 2048.4576 | 2426.0456 | 5849.3107 | 8099.6371 | 10684.5266 | 2873.3059 | 49447.2826 | 0
SC03 | Soft Costs | Landscape Designer | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SC04 | Soft Costs | Structure Engineer | 2308.7174 | 1309.641 | 1679.7521 | 621.3761 | 735.9131 | 1774.3213 | 2456.932 | 3241.0286 | 871.5844 | 14999.2659 | 0
SC05 | Soft Costs | MEP Consultant | 1204.683 | 683.3674 | 876.4905 | 324.2325 | 383.9976 | 925.8365 | 1282.0211 | 1691.1607 | 454.7906 | 7826.58 | 0
SC06 | Soft Costs | Quantity Surveyor | 2286.0034 | 1296.7562 | 1663.2261 | 615.2628 | 728.6729 | 1756.8649 | 2432.7598 | 3209.1422 | 863.0094 | 14851.6977 | 0
SC07 | Soft Costs | Notary | 3323.9255 | 1442.309 | 1999.5321 | 986.4646 | 1012.3485 | 4273.0022 | 6582.4222 | 9146.3673 | 737.6914 | 29504.0626 | 0
SC08 | Soft Costs | Tax & legal advice | 4597.0788 | 4877.0114 | 4350.8067 | 1313.4511 | 0 | 0 | 0 | 0 | 3279.0487 | 18417.3967 | 0
SC09 | Soft Costs | Other professional fees | 6156.881 | 3492.5468 | 4479.5582 | 1657.0841 | 1962.531 | 4731.755 | 6552.1393 | 8643.1659 | 2324.3388 | 40000 | 0
SC10 | Soft Costs | Land Survey | 30.7937 | 13.3619 | 18.5242 | 9.1389 | 9.3787 | 39.5862 | 60.9813 | 84.7343 | 6.8342 | 273.3333 | 0
SC11 | Soft Costs | Soil Test | 1365.3108 | 592.4321 | 821.3129 | 405.1928 | 415.8247 | 1755.1465 | 2703.7466 | 3756.8936 | 303.0086 | 12118.8687 | 0
SC12 | Soft Costs | MEP Engineering | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SC13 | Soft Costs | Sitegrid / Other QS | 920.4964 | 522.16 | 669.725 | 247.7456 | 0 | 0 | 0 | 0 | 347.5048 | 2707.6317 | 0
PM01 | Project Management | Staff | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
PM02 | Project Management | A&G Allocation | 112188.0096 | 63639.6704 | 81624.5627 | 30194.6662 | 0 | 0 | 0 | 0 | 42353.091 | 330000 | 0
PM03 | Project Management | Project Management | 80.0954 | 45.4348 | 58.2749 | 21.5571 | 0 | 0 | 0 | 0 | 30.2375 | 235.5998 | 0
PM04 | Contingency | Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
HC08 | Hard Costs | Interior Cost | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
LC01 | Land | Land Costs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TX01 | Income Tax | Income tax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TX02 | Sales Tax | Sales VAT | 10959.4301 | 11626.7892 | 10372.3178 | 3131.2658 | 0 | 0 | 0 | 0 | 7817.248 | 43907.0509 | 0
OC01 | Other Costs | Bank fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OC02 | Other Costs | Withholding tax | 16.6284 | 9.4326 | 12.0983 | 4.4754 | 0 | 0 | 0 | 0 | 6.2775 | 48.9123 | 0
OC03 | Other Costs | Miscellaneous | 213.7726 | 121.2644 | 155.5344 | 57.5355 | 0 | 0 | 0 | 0 | 80.7032 | 628.81 | 0
OC04 | Other Costs | Unmapped | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  | 187629.339 | 113484.3039 | 139323.2698 | 50887.4205 | 18629.1703 | 47517.5399 | 66743.3802 | 88701.4549 | 75322.6714 | 788238.5499 | 0
EAC allocation | EAC allocation | EAC allocation | EAC allocation | EAC allocation | EAC allocation | EAC allocation | EAC allocation | EAC allocation | EAC allocation | EAC allocation | EAC allocation | EAC allocation | EAC allocation
HC01 | Hard Costs | Preliminaries | 128399.4728 | 81336.5868 | 115186.5002 | 41970.7251 | 0 | 0 | 0 | 0 | 39621.2 | 406514.4849 | 0
HC02 | Hard Costs | Structure & Architecture | 1173228.4947 | 774648.8294 | 1160416.3677 | 458986.3067 | 0 | 0 | 0 | 0 | 400227.1517 | 3967507.1502 | 0
HC03 | Hard Costs | MEP | 275221.984 | 181045.7299 | 180233.8656 | 98776.8182 | 0 | 0 | 0 | 0 | 103648.0038 | 838926.4015 | 0
HC04 | Hard Costs | Provisional Sum | 25160 | 25160 | 25160 | 25160 | 0 | 0 | 0 | 0 | 25160 | 125800 | 0
HC05 | Hard Costs | Landscaping | 35000 | 35000 | 35000 | 35000 | 0 | 0 | 0 | 0 | 35000 | 175000 | 0
HC06 | Hard Costs | Network & Infrastructure upgrade | 152201.7331 | 86337.8196 | 110737.3235 | 40964.0972 | 0 | 0 | 0 | 0 | 57459.0267 | 447700 | 0
HC07 | Hard Costs | New Infrastructure | 47536.9607 | 26965.774 | 34586.4379 | 12794.2609 | 0 | 0 | 0 | 0 | 17946.0998 | 139829.5333 | 0
SC01 | Soft Costs | Architect Cost | 45192.2831 | 25635.7343 | 32880.5222 | 12163.2063 | 14405.2249 | 34731.6785 | 48093.5293 | 63441.9279 | 17060.9398 | 293605.0464 | 0
SC02 | Soft Costs | Interior Designer | 27822.1168 | 15782.3492 | 20242.5208 | 7488.1401 | 8868.4134 | 21382.1642 | 29608.2361 | 39057.3037 | 10503.3742 | 180754.6185 | 0
SC03 | Soft Costs | Landscape Designer | 4681.1444 | 2655.4218 | 3405.8574 | 1259.8993 | 1492.1339 | 3597.6054 | 4981.6637 | 6571.4942 | 1767.2204 | 30412.4403 | 0
SC04 | Soft Costs | Structure Engineer | 5192.303 | 2945.3811 | 3777.7607 | 1397.4743 | 1655.0678 | 3990.4467 | 5525.6375 | 7289.0699 | 1960.1924 | 33733.3333 | 0
SC05 | Soft Costs | MEP Consultant | 1742.7052 | 988.5654 | 1267.9389 | 469.0377 | 555.4944 | 1339.3232 | 1854.583 | 2446.4481 | 657.9041 | 11322 | 0
SC06 | Soft Costs | Quantity Surveyor | 14940.1885 | 8474.9581 | 10870.024 | 4021.0537 | 4762.2462 | 11482.0007 | 15899.3162 | 20973.3676 | 5640.2031 | 97063.358 | 0
SC07 | Soft Costs | Notary | 14059.1042 | 6100.4895 | 8457.3586 | 4172.4186 | 4281.8989 | 18073.3845 | 27841.4664 | 38686.1053 | 3120.1906 | 124792.4167 | 0
SC08 | Soft Costs | Tax & legal advice | 4597.0788 | 4877.0114 | 4350.8067 | 1313.4511 | 0 | 0 | 0 | 0 | 3279.0487 | 18417.3967 | 0
SC09 | Soft Costs | Other professional fees | 6156.881 | 3492.5468 | 4479.5582 | 1657.0841 | 1962.531 | 4731.755 | 6552.1393 | 8643.1659 | 2324.3388 | 40000 | 0
SC10 | Soft Costs | Land Survey | 1266.07 | 549.3698 | 761.6138 | 375.7404 | 385.5995 | 1627.5695 | 2507.2184 | 3483.8149 | 280.9837 | 11237.98 | 0
SC11 | Soft Costs | Soil Test | 3475.6263 | 1508.1346 | 2090.7888 | 1031.4859 | 1058.5511 | 4468.0179 | 6882.8377 | 9563.7988 | 771.359 | 30850.6 | 0
SC12 | Soft Costs | MEP Engineering | 4681.1444 | 2655.4218 | 3405.8574 | 1259.8993 | 1492.1339 | 3597.6054 | 4981.6637 | 6571.4942 | 1767.2204 | 30412.4403 | 0
SC13 | Soft Costs | Sitegrid / Other QS | 920.4964 | 522.16 | 669.725 | 247.7456 | 0 | 0 | 0 | 0 | 347.5048 | 2707.6317 | 0
PM01 | Project Management | Staff | 42902.9568 | 24337.0931 | 31214.8785 | 11547.0491 | 0 | 0 | 0 | 0 | 16196.6759 | 126198.6533 | 0
PM02 | Project Management | A&G Allocation | 308517.0265 | 175009.0937 | 224467.5475 | 83035.3321 | 0 | 0 | 0 | 0 | 116471.0001 | 907500 | 0
PM03 | Project Management | Project Management | 80.0954 | 45.4348 | 58.2749 | 21.5571 | 0 | 0 | 0 | 0 | 30.2375 | 235.5998 | 0
PM04 | Contingency | Contingency | 405335.1453 | 229930.0536 | 294909.4481 | 109093.2932 | 0 | 0 | 0 | 0 | 153021.6672 | 1192289.6073 | 0
HC08 | Hard Costs | Interior Cost | 142688 | 105074.6667 | 141353.3333 | 77868 | 0 | 0 | 0 | 0 | 92829.3333 | 559813.3333 | 0
LC01 | Land | Land Costs | 69345 | 30090 | 41715 | 20580 | 0 | 0 | 0 | 0 | 15390 | 177120 | 0
TX01 | Income Tax | Income tax | 70000 | 74262.5513 | 66250 | 20000 | 0 | 0 | 0 | 0 | 49930.275 | 280442.8263 | 0
TX02 | Sales Tax | Sales VAT | 308000 | 326755.2259 | 291500 | 88000 | 0 | 0 | 0 | 0 | 219693.21 | 1233948.4359 | 0
OC01 | Other Costs | Bank fees | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
OC02 | Other Costs | Withholding tax | 16.6284 | 9.4326 | 12.0983 | 4.4754 | 0 | 0 | 0 | 0 | 6.2775 | 48.9123 | 0
OC03 | Other Costs | Miscellaneous | 213.7726 | 121.2644 | 155.5344 | 57.5355 | 0 | 0 | 0 | 0 | 80.7032 | 628.81 | 0
OC04 | Other Costs | Unmapped | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL |  |  | 3318574.412 | 2252317.0996 | 2849616.9426 | 1160716.0867 | 40919.295 | 109021.5511 | 154728.2913 | 206727.9904 | 1392191.3415 | 11484813.0103 | 0

## Villas
Kalindo Cove - Villa Register
Physical drivers, sales assumptions, allocation factors, and unit status.
← Back to Cover
Villa ID | Cluster | Villa | Buyer | Status | Phase 1 | Building m² | Outdoor m² | Total buildup m² | Land plot m² | Net sale price USD | Delayed income USD | Gross cash budget USD | Building factor | Outdoor factor | Buildup factor | Land factor
V01 | Horizon Villas | Horizon Ridge Top | Thomas Whitfield | Sold / Contracted | Yes | 858.7 | 823.6 | 1682.3 | 4623 | 2800000 | 300000 | 3108000 | 15.05% | 15.77% | 15.39% | 11.27%
V02 | Horizon Villas | Horizon Ridge 3BDR | Grant & Petra | Sold / Contracted | Yes | 545.6 | 408.7 | 954.3 | 2006 | 2970502.0537 | 0 | 3297257.2796 | 9.563% | 7.824% | 8.731% | 4.889%
V03 | Horizon Villas | 4BDR Canopy House | Annelie | Sold / Contracted | Yes | 589.69 | 634.3 | 1223.99 | 2781 | 2650000 | 0 | 2941500 | 10.34% | 12.14% | 11.2% | 6.777%
V04 | Horizon Villas | Meadow 1 | Julien | Sold / Contracted | Yes | 288.78 | 164 | 452.78 | 1372 | 800000 | 550000 | 888000 | 5.061% | 3.139% | 4.143% | 3.343%
V05 | Horizon Villas | Meadow 2 |  | Unsold | No | 328.04 | 208.2 | 536.24 | 1408 | 0 | 0 | 0 | 5.749% | 3.985% | 4.906% | 3.431%
V06 | Palm Valley | Palm Valley/E1 |  | Unsold | No | 686.4 | 606.5 | 1292.9 | 5943 | 0 | 0 | 0 | 12.03% | 11.61% | 11.83% | 14.48%
V07 | Palm Valley | Palm Valley/E2 |  | Unsold | No | 929.4 | 860.9 | 1790.3 | 9155 | 0 | 0 | 0 | 16.29% | 16.48% | 16.38% | 22.31%
V08 | Palm Valley | Palm Valley/E3 |  | Unsold | No | 1129.35 | 1232.3 | 2361.65 | 12721 | 0 | 0 | 0 | 19.79% | 23.59% | 21.61% | 31%
V09 | Horizon Villas | Kiri 3 | TBD | TBD | Yes | 349.6 | 285.5 | 635.1 | 1026 | 1997211 | 0 | 2216904.21 | 6.127% | 5.465% | 5.811% | 2.5%
Driver checks | Driver checks | Driver checks | Driver checks | Driver checks
Check | Actual | Expected | Difference | Status
Building factor | 1 | 1 | 0 | PASS
Outdoor factor | 1 | 1 | 0 | PASS
Buildup factor | 1 | 1 | 0 | PASS
Land factor | 1 | 1 | 0 | PASS
Phase 1 villa count | 5 | 5 | 0 | PASS

## Sales Plan
Kalindo Cove - Sales Receipt Plan | [8 empty] | ← Back to Cover
Remaining gross contract receipts are distributed across four editable forecast milestones; actual receipts are ledger-linked.
← Back to Cover
Villa | Milestone | Forecast Date | % of Remaining | Gross Cash Budget USD | Actual Received USD | Remaining Receipts USD | Planned Receipt USD | Check
Horizon Ridge Top | M1 | 2024-01-01 | 30% | 3108000 | 443990 | 2664010 | 799203 | 0%
Horizon Ridge Top | M2 | 2024-07-01 | 20% | 3108000 | 443990 | 2664010 | 532802 | 0%
Horizon Ridge Top | M3 | 2025-01-01 | 30% | 3108000 | 443990 | 2664010 | 799203 | 0%
Horizon Ridge Top | M4 | 2025-07-01 | 20% | 3108000 | 443990 | 2664010 | 532802 | 0%
Horizon Ridge 3BDR | M1 | 2024-01-01 | 30% | 3297257.2796 | 0 | 3297257.2796 | 989177.1839 | 0%
Horizon Ridge 3BDR | M2 | 2024-07-01 | 20% | 3297257.2796 | 0 | 3297257.2796 | 659451.4559 | 0%
Horizon Ridge 3BDR | M3 | 2025-01-01 | 30% | 3297257.2796 | 0 | 3297257.2796 | 989177.1839 | 0%
Horizon Ridge 3BDR | M4 | 2025-07-01 | 20% | 3297257.2796 | 0 | 3297257.2796 | 659451.4559 | 0%
4BDR Canopy House | M1 | 2024-01-01 | 30% | 2941500 | 0 | 2941500 | 882450 | 0%
4BDR Canopy House | M2 | 2024-07-01 | 20% | 2941500 | 0 | 2941500 | 588300 | 0%
4BDR Canopy House | M3 | 2025-01-01 | 30% | 2941500 | 0 | 2941500 | 882450 | 0%
4BDR Canopy House | M4 | 2025-07-01 | 20% | 2941500 | 0 | 2941500 | 588300 | 0%
Meadow 1 | M1 | 2024-01-01 | 30% | 888000 | 388541.8 | 499458.2 | 149837.46 | 0%
Meadow 1 | M2 | 2024-07-01 | 20% | 888000 | 388541.8 | 499458.2 | 99891.64 | 0%
Meadow 1 | M3 | 2025-01-01 | 30% | 888000 | 388541.8 | 499458.2 | 149837.46 | 0%
Meadow 1 | M4 | 2025-07-01 | 20% | 888000 | 388541.8 | 499458.2 | 99891.64 | 0%
Meadow 2 | M1 | 2024-01-01 | 30% | 0 | 0 | 0 | 0 | 0%
Meadow 2 | M2 | 2024-07-01 | 20% | 0 | 0 | 0 | 0 | 0%
Meadow 2 | M3 | 2025-01-01 | 30% | 0 | 0 | 0 | 0 | 0%
Meadow 2 | M4 | 2025-07-01 | 20% | 0 | 0 | 0 | 0 | 0%
Palm Valley/E1 | M1 | 2024-01-01 | 30% | 0 | 0 | 0 | 0 | 0%
Palm Valley/E1 | M2 | 2024-07-01 | 20% | 0 | 0 | 0 | 0 | 0%
Palm Valley/E1 | M3 | 2025-01-01 | 30% | 0 | 0 | 0 | 0 | 0%
Palm Valley/E1 | M4 | 2025-07-01 | 20% | 0 | 0 | 0 | 0 | 0%
Palm Valley/E2 | M1 | 2024-01-01 | 30% | 0 | 0 | 0 | 0 | 0%
Palm Valley/E2 | M2 | 2024-07-01 | 20% | 0 | 0 | 0 | 0 | 0%
Palm Valley/E2 | M3 | 2025-01-01 | 30% | 0 | 0 | 0 | 0 | 0%
Palm Valley/E2 | M4 | 2025-07-01 | 20% | 0 | 0 | 0 | 0 | 0%
Palm Valley/E3 | M1 | 2024-01-01 | 30% | 0 | 0 | 0 | 0 | 0%
Palm Valley/E3 | M2 | 2024-07-01 | 20% | 0 | 0 | 0 | 0 | 0%
Palm Valley/E3 | M3 | 2025-01-01 | 30% | 0 | 0 | 0 | 0 | 0%
Palm Valley/E3 | M4 | 2025-07-01 | 20% | 0 | 0 | 0 | 0 | 0%
Kiri 3 | M1 | 2024-01-01 | 30% | 2216904.21 | 0 | 2216904.21 | 665071.263 | 0%
Kiri 3 | M2 | 2024-07-01 | 20% | 2216904.21 | 0 | 2216904.21 | 443380.842 | 0%
Kiri 3 | M3 | 2025-01-01 | 30% | 2216904.21 | 0 | 2216904.21 | 665071.263 | 0%
Kiri 3 | M4 | 2025-07-01 | 20% | 2216904.21 | 0 | 2216904.21 | 443380.842 | 0%
Villa receipt control | Villa receipt control | Villa receipt control | Villa receipt control | Villa receipt control | Villa receipt control
Villa | Gross Budget | Actual Received | Forecast Planned | Difference | Status
Horizon Ridge Top | 3108000 | 443990 | 2664010 | 0 | PASS
Horizon Ridge 3BDR | 3297257.2796 | 0 | 3297257.2796 | 0 | PASS
4BDR Canopy House | 2941500 | 0 | 2941500 | 0 | PASS
Meadow 1 | 888000 | 388541.8 | 499458.2 | 0 | PASS
Meadow 2 | 0 | 0 | 0 | 0 | PASS
Palm Valley/E1 | 0 | 0 | 0 | 0 | PASS
Palm Valley/E2 | 0 | 0 | 0 | 0 | PASS
Palm Valley/E3 | 0 | 0 | 0 | 0 | PASS
Kiri 3 | 2216904.21 | 0 | 2216904.21 | 0 | PASS

## Budget
Kalindo Cove - Development Budget | [8 empty] | ← Back to Cover
Central budget and schedule assumptions. Direct unit estimates are shown on the right; EAC updates automatically from actual outflows.
← Back to Cover | [13 empty] | Direct unit inputs (USD) | Direct unit inputs (USD) | Direct unit inputs (USD) | Direct unit inputs (USD) | Direct unit inputs (USD) | Direct unit inputs (USD) | Direct unit inputs (USD) | Direct unit inputs (USD) | Direct unit inputs (USD) | Eligible villas (1 = include) | Eligible villas (1 = include) | Eligible villas (1 = include) | Eligible villas (1 = include) | Eligible villas (1 = include) | Eligible villas (1 = include) | Eligible villas (1 = include) | Eligible villas (1 = include) | Eligible villas (1 = include) | Allocation helpers
Budget ID | Section | Category | In Unit P&L | Allocation Basis | Input Amount USD | Total Budget USD | Actual Paid USD | Remaining USD | EAC USD | Schedule Start | Schedule End | Forecast Months | Source / Notes | Horizon Ridge Top | Horizon Ridge 3BDR | 4BDR Canopy House | Meadow 1 | Meadow 2 | Palm Valley/E1 | Palm Valley/E2 | Palm Valley/E3 | Kiri 3 | Horizon Ridge Top2 | Horizon Ridge 3BDR3 | 4BDR Canopy House4 | Meadow 15 | Meadow 26 | Palm Valley/E17 | Palm Valley/E28 | Palm Valley/E39 | Kiri 310 | Direct Denom | Building Denom | Plot Denom | Revenue Denom | Equal Denom | Selected Denom | Horizon Ridge Top Weight | Horizon Ridge 3BDR Weight | 4BDR Canopy House Weight | Meadow 1 Weight | Meadow 2 Weight | Palm Valley/E1 Weight | Palm Valley/E2 Weight | Palm Valley/E3 Weight | Kiri 3 Weight | Check
HC01 | Hard Costs | Preliminaries | Yes | Direct | 0 | 406514.4849 | 0 | 406514.4849 | 406514.4849 | 2024-01-01 | 2025-07-01 | 19 | Phase 1 direct estimate | 128399.4728 | 81336.5868 | 115186.5002 | 41970.7251 | 0 | 0 | 0 | 0 | 39621.2 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 406514.4849 | 4948.47 | 11808 | 11217713.0537 | 5 | 406514.4849 | 31.59% | 20.01% | 28.34% | 10.32% | 0% | 0% | 0% | 0% | 9.747% | 100%
HC02 | Hard Costs | Structure & Architecture | Yes | Direct | 0 | 3967507.1502 | 0 | 3967507.1502 | 3967507.1502 | 2024-02-01 | 2025-07-01 | 18 | Phase 1 direct estimate | 1173228.4947 | 774648.8294 | 1160416.3677 | 458986.3067 | 0 | 0 | 0 | 0 | 400227.1517 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 3967507.1502 | 4948.47 | 11808 | 11217713.0537 | 5 | 3967507.1502 | 29.57% | 19.52% | 29.25% | 11.57% | 0% | 0% | 0% | 0% | 10.09% | 100%
HC03 | Hard Costs | MEP | Yes | Direct | 0 | 838926.4015 | 0 | 838926.4015 | 838926.4015 | 2024-02-01 | 2025-07-01 | 18 | Phase 1 direct estimate | 275221.984 | 181045.7299 | 180233.8656 | 98776.8182 | 0 | 0 | 0 | 0 | 103648.0038 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 838926.4015 | 4948.47 | 11808 | 11217713.0537 | 5 | 838926.4015 | 32.81% | 21.58% | 21.48% | 11.77% | 0% | 0% | 0% | 0% | 12.35% | 100%
HC04 | Hard Costs | Provisional Sum | Yes | Direct | 0 | 125800 | 0 | 125800 | 125800 | 2024-02-01 | 2025-07-01 | 18 | Phase 1 direct estimate | 25160 | 25160 | 25160 | 25160 | 0 | 0 | 0 | 0 | 25160 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 125800 | 4948.47 | 11808 | 11217713.0537 | 5 | 125800 | 20% | 20% | 20% | 20% | 0% | 0% | 0% | 0% | 20% | 100%
HC05 | Hard Costs | Landscaping | Yes | Direct | 0 | 175000 | 0 | 175000 | 175000 | 2024-08-01 | 2025-07-01 | 12 | Phase 1 direct estimate | 35000 | 35000 | 35000 | 35000 | 0 | 0 | 0 | 0 | 35000 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 175000 | 4948.47 | 11808 | 11217713.0537 | 5 | 175000 | 20% | 20% | 20% | 20% | 0% | 0% | 0% | 0% | 20% | 100%
HC06 | Hard Costs | Network & Infrastructure upgrade | Yes | Direct | 0 | 447700 | 0 | 447700 | 447700 | 2024-01-01 | 2024-06-01 | 6 | Phase 1 direct estimate | 152201.7331 | 86337.8196 | 110737.3235 | 40964.0972 | 0 | 0 | 0 | 0 | 57459.0267 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 447700 | 4948.47 | 11808 | 11217713.0537 | 5 | 447700 | 34% | 19.28% | 24.73% | 9.15% | 0% | 0% | 0% | 0% | 12.83% | 100%
HC07 | Hard Costs | New Infrastructure | Yes | Direct | 0 | 139829.5333 | 0 | 139829.5333 | 139829.5333 | 2024-01-01 | 2024-06-01 | 6 | Source schedule | 47536.9607 | 26965.774 | 34586.4379 | 12794.2609 | 0 | 0 | 0 | 0 | 17946.0998 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 139829.5333 | 4948.47 | 11808 | 11217713.0537 | 5 | 139829.5333 | 34% | 19.28% | 24.73% | 9.15% | 0% | 0% | 0% | 0% | 12.83% | 100%
SC01 | Soft Costs | Architect Cost | Yes | Building | 293605.0464 | 293605.0464 | 223272.0577 | 70332.9887 | 293605.0464 | 2024-01-01 | 2024-12-01 | 12 | Source: Cost Allocation tab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 10929.56 | 41035 | 11217713.0537 | 9 | 10929.56 | 15.39% | 8.731% | 11.2% | 4.143% | 4.906% | 11.83% | 16.38% | 21.61% | 5.811% | 100%
SC02 | Soft Costs | Interior Designer | Yes | Building | 180754.6185 | 180754.6185 | 49447.2826 | 131307.3358 | 180754.6185 | 2024-01-01 | 2024-12-01 | 12 | Includes SDK budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 10929.56 | 41035 | 11217713.0537 | 9 | 10929.56 | 15.39% | 8.731% | 11.2% | 4.143% | 4.906% | 11.83% | 16.38% | 21.61% | 5.811% | 100%
SC03 | Soft Costs | Landscape Designer | Yes | Building | 30412.4403 | 30412.4403 | 0 | 30412.4403 | 30412.4403 | 2024-01-01 | 2024-12-01 | 12 | Source: Cost Allocation tab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 10929.56 | 41035 | 11217713.0537 | 9 | 10929.56 | 15.39% | 8.731% | 11.2% | 4.143% | 4.906% | 11.83% | 16.38% | 21.61% | 5.811% | 100%
SC04 | Soft Costs | Structure Engineer | Yes | Building | 33733.3333 | 33733.3333 | 14999.2659 | 18734.0675 | 33733.3333 | 2024-01-01 | 2024-12-01 | 12 | Source: Cost Allocation tab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 10929.56 | 41035 | 11217713.0537 | 9 | 10929.56 | 15.39% | 8.731% | 11.2% | 4.143% | 4.906% | 11.83% | 16.38% | 21.61% | 5.811% | 100%
SC05 | Soft Costs | MEP Consultant | Yes | Building | 11322 | 11322 | 7826.58 | 3495.42 | 11322 | 2024-01-01 | 2024-12-01 | 12 | Source: Cost Allocation tab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 10929.56 | 41035 | 11217713.0537 | 9 | 10929.56 | 15.39% | 8.731% | 11.2% | 4.143% | 4.906% | 11.83% | 16.38% | 21.61% | 5.811% | 100%
SC06 | Soft Costs | Quantity Surveyor | Yes | Building | 97063.358 | 97063.358 | 14851.6977 | 82211.6603 | 97063.358 | 2024-01-01 | 2025-07-01 | 19 | Source: Cost Allocation tab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 10929.56 | 41035 | 11217713.0537 | 9 | 10929.56 | 15.39% | 8.731% | 11.2% | 4.143% | 4.906% | 11.83% | 16.38% | 21.61% | 5.811% | 100%
SC07 | Soft Costs | Notary | Yes | Plot | 124792.4167 | 124792.4167 | 29504.0626 | 95288.354 | 124792.4167 | 2024-01-01 | 2024-12-01 | 12 | Source: Cost Allocation tab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 10929.56 | 41035 | 11217713.0537 | 9 | 41035 | 11.27% | 4.889% | 6.777% | 3.343% | 3.431% | 14.48% | 22.31% | 31% | 2.5% | 100%
SC08 | Soft Costs | Tax & legal advice | Yes | Revenue | 17941.97 | 17941.97 | 18417.3967 | 0 | 18417.3967 | 2024-01-01 | 2024-12-01 | 12 | Source: Cost Allocation tab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 10929.56 | 41035 | 11217713.0537 | 9 | 11217713.0537 | 24.96% | 26.48% | 23.62% | 7.132% | 0% | 0% | 0% | 0% | 17.8% | 100%
SC09 | Soft Costs | Other professional fees | Yes | Building | 40000 | 40000 | 40000 | 0 | 40000 | 2024-01-01 | 2024-12-01 | 12 | Source: Cost Allocation tab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 10929.56 | 41035 | 11217713.0537 | 9 | 10929.56 | 15.39% | 8.731% | 11.2% | 4.143% | 4.906% | 11.83% | 16.38% | 21.61% | 5.811% | 100%
SC10 | Soft Costs | Land Survey | Yes | Plot | 11237.98 | 11237.98 | 273.3333 | 10964.6467 | 11237.98 | 2024-01-01 | 2024-06-01 | 6 | Source: Cost Allocation tab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 10929.56 | 41035 | 11217713.0537 | 9 | 41035 | 11.27% | 4.889% | 6.777% | 3.343% | 3.431% | 14.48% | 22.31% | 31% | 2.5% | 100%
SC11 | Soft Costs | Soil Test | Yes | Plot | 30850.6 | 30850.6 | 12118.8687 | 18731.7313 | 30850.6 | 2024-01-01 | 2024-06-01 | 6 | Source: Cost Allocation tab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 10929.56 | 41035 | 11217713.0537 | 9 | 41035 | 11.27% | 4.889% | 6.777% | 3.343% | 3.431% | 14.48% | 22.31% | 31% | 2.5% | 100%
SC12 | Soft Costs | MEP Engineering | Yes | Building | 30412.4403 | 30412.4403 | 0 | 30412.4403 | 30412.4403 | 2024-01-01 | 2024-12-01 | 12 | Source: Cost Allocation tab | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 0 | 10929.56 | 41035 | 11217713.0537 | 9 | 10929.56 | 15.39% | 8.731% | 11.2% | 4.143% | 4.906% | 11.83% | 16.38% | 21.61% | 5.811% | 100%
SC13 | Soft Costs | Sitegrid / Other QS | Yes | Building | 0 | 0 | 2707.6317 | 0 | 2707.6317 | 2024-01-01 | 2024-12-01 | 12 | Actual-only category | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 4948.47 | 11808 | 11217713.0537 | 5 | 4948.47 | 34% | 19.28% | 24.73% | 9.15% | 0% | 0% | 0% | 0% | 12.83% | 100%
PM01 | Project Management | Staff | Yes | Building | 126198.6533 | 126198.6533 | 0 | 126198.6533 | 126198.6533 | 2024-01-01 | 2025-09-01 | 21 | Source: staffing schedule | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 4948.47 | 11808 | 11217713.0537 | 5 | 4948.47 | 34% | 19.28% | 24.73% | 9.15% | 0% | 0% | 0% | 0% | 12.83% | 100%
PM02 | Project Management | A&G Allocation | Yes | Building | 907500 | 907500 | 330000 | 577500 | 907500 | 2024-01-01 | 2025-09-01 | 21 | Source: A&G allocation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 4948.47 | 11808 | 11217713.0537 | 5 | 4948.47 | 34% | 19.28% | 24.73% | 9.15% | 0% | 0% | 0% | 0% | 12.83% | 100%
PM03 | Project Management | Project Management | Yes | Building | 0 | 0 | 235.5998 | 0 | 235.5998 | 2024-01-01 | 2025-09-01 | 21 | Actual-only reimbursements | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 4948.47 | 11808 | 11217713.0537 | 5 | 4948.47 | 34% | 19.28% | 24.73% | 9.15% | 0% | 0% | 0% | 0% | 12.83% | 100%
PM04 | Contingency | Contingency | Yes | Building | 0 | 1192289.6073 | 0 | 1192289.6073 | 1192289.6073 | 2024-02-01 | 2025-07-01 | 18 | 20% of core hard costs; excludes new infrastructure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 4948.47 | 11808 | 11217713.0537 | 5 | 4948.47 | 34% | 19.28% | 24.73% | 9.15% | 0% | 0% | 0% | 0% | 12.83% | 100%
HC08 | Hard Costs | Interior Cost | Yes | Direct | 0 | 559813.3333 | 0 | 559813.3333 | 559813.3333 | 2024-08-01 | 2025-06-01 | 11 | FF&E estimate | 142688 | 105074.6667 | 141353.3333 | 77868 | 0 | 0 | 0 | 0 | 92829.3333 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 559813.3333 | 4948.47 | 11808 | 11217713.0537 | 5 | 559813.3333 | 25.49% | 18.77% | 25.25% | 13.91% | 0% | 0% | 0% | 0% | 16.58% | 100%
LC01 | Land | Land Costs | Yes | Plot | 177120 | 177120 | 0 | 177120 | 177120 | 2025-12-01 | 2025-12-01 | 1 | Cash-flow land budget | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 4948.47 | 11808 | 11217713.0537 | 5 | 11808 | 39.15% | 16.99% | 23.55% | 11.62% | 0% | 0% | 0% | 0% | 8.689% | 100%
TX01 | Income Tax | Income tax | Yes | Revenue | 0 | 280442.8263 | 0 | 280442.8263 | 280442.8263 | 2025-12-01 | 2025-12-01 | 1 | 2.5% of net contracted villa sales | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 4948.47 | 11808 | 11217713.0537 | 5 | 11217713.0537 | 24.96% | 26.48% | 23.62% | 7.132% | 0% | 0% | 0% | 0% | 17.8% | 100%
TX02 | Sales Tax | Sales VAT | No | Revenue | 0 | 1233948.4359 | 43907.0509 | 1190041.385 | 1233948.4359 | 2024-01-01 | 2025-07-01 | 19 | Cash-only VAT remittance tied to forecast receipts | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 4948.47 | 11808 | 11217713.0537 | 5 | 11217713.0537 | 24.96% | 26.48% | 23.62% | 7.132% | 0% | 0% | 0% | 0% | 17.8% | 100%
OC01 | Other Costs | Bank fees | Yes | Building | 0 | 0 | 0 | 0 | 0 | 2024-01-01 | 2025-12-01 | 24 | Actual-only | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 4948.47 | 11808 | 11217713.0537 | 5 | 4948.47 | 34% | 19.28% | 24.73% | 9.15% | 0% | 0% | 0% | 0% | 12.83% | 100%
OC02 | Other Costs | Withholding tax | Yes | Building | 0 | 0 | 48.9123 | 0 | 48.9123 | 2024-01-01 | 2025-12-01 | 24 | Actual-only | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 4948.47 | 11808 | 11217713.0537 | 5 | 4948.47 | 34% | 19.28% | 24.73% | 9.15% | 0% | 0% | 0% | 0% | 12.83% | 100%
OC03 | Other Costs | Miscellaneous | Yes | Building | 0 | 0 | 628.81 | 0 | 628.81 | 2024-01-01 | 2025-12-01 | 24 | Actual-only | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 4948.47 | 11808 | 11217713.0537 | 5 | 4948.47 | 34% | 19.28% | 24.73% | 9.15% | 0% | 0% | 0% | 0% | 12.83% | 100%
OC04 | Other Costs | Unmapped | Yes | Building | 0 | 0 | 0 | 0 | 0 | 2024-01-01 | 2025-12-01 | 24 | Control category; expected to remain zero | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | 0 | 4948.47 | 11808 | 11217713.0537 | 5 | 4948.47 | 34% | 19.28% | 24.73% | 9.15% | 0% | 0% | 0% | 0% | 12.83% | 100%
TOTAL DEVELOPMENT BUDGET | [5 empty] | 11480716.6297 | 788238.5499 | 10696574.4604 | 11484813.0103
Note on F14: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: legacy Cost Allocation summary. This is a genuine source input, not a derived value.
Note on G30: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Formula: contingency rate multiplied by the six core hard-cost categories, matching the legacy model logic.
Note on G33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Formula: net contracted sales multiplied by the Income Tax assumption.
Note on G34: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Cash-only VAT budget. Excluded from Unit P&L and linked to gross forecast sales receipts in Cash Flow.

## Inputs
Kalindo Cove - Model Inputs
Blue-font cells are editable assumptions; source data is retained as black hardcodes; formulas are black/green.
Core assumptions | Core assumptions | Core assumptions | Core assumptions | Monthly FX assumptions | Monthly FX assumptions | Monthly FX assumptions | Category mapping |  |  |  | ← Back to Cover
Assumption | Value | Units | Source / rationale | Year | Month | Average IDR / USD | Original Type | Standard Category | Treatment | Review Note
Fallback IDR / USD | 15000 | IDR per USD | Source Info tab | 2022-01-01 | 2022-01 | 14381 | A&G Allocation | A&G Allocation | Cash outflow
VAT rate | 11% | % | Source Info tab | 2022-02-01 | 2022-02 | 14371 | Architect Common cost | Architect Cost | Cash outflow
Contingency rate | 20% | % | Source Info tab; applied to core hard costs | 2022-03-01 | 2022-03 | 14349 | Architect Cost | Architect Cost | Cash outflow
Income tax rate | 2.5% | % of net contracted sales | Implied by prior P&L | 2022-04-01 | 2022-04 | 14418 | Land Survey | Land Survey | Cash outflow
Model start | 2022-02-01 | Month start | Prior cash-flow horizon | 2022-05-01 | 2022-05 | 14544 | MEP Consultant | MEP Consultant | Cash outflow
Actuals through | 2023-12-31 | Month end | Latest actual period | 2022-06-01 | 2022-06 | 14848 | Marketing & Sales | Interior Designer | Cash outflow
First forecast month | 2024-01-01 | Month start | Derived from actuals cut-off | 2022-07-01 | 2022-07 | 14958 | Miscellaneous | Miscellaneous | Cash outflow
Opening operational cash | 0 | USD | Prior cash-flow convention | 2022-08-01 | 2022-08 | 14875 | Notary | Notary | Cash outflow
|  |  |  | 2022-09-01 | 2022-09 | 15247 | Other professional fees | Other professional fees | Cash outflow
Model conventions | Model conventions | Model conventions | Model conventions | 2022-10-01 | 2022-10 | 15542 | Project Management | Project Management | Cash outflow
Convention | Policy | Owner | Status | 2022-11-01 | 2022-11 | 15737 | Project Management Costs | Project Management | Cash outflow
Currency | USD reporting; IDR source transactions translated at monthly average FX | Finance | Active | 2022-12-01 | 2022-12 | 15731 | Quantity Surveyor | Quantity Surveyor | Cash outflow
Actual / Forecast | Periods through 2023-12 are Actual; Jan 2024 onward is Forecast | Finance | Active | 2023-01-01 | 2023-01 | 14979 | Sitegrid? | Sitegrid / Other QS | Cash outflow
Cash signs | Inflows positive; outflows shown as positive costs; net cash flow = inflows - outflows | Finance | Active | 2023-02-01 | 2023-02 | 15274 | Soil Test | Soil Test | Cash outflow
Budget EAC | EAC = Actual paid + max(Budget - Actual paid, 0) | Finance | Active | 2023-03-01 | 2023-03 | 15062 | Structure Engineer | Structure Engineer | Cash outflow
Unit allocation | Direct estimates where available; otherwise driver-weighted across eligible villas | Development | Active | 2023-04-01 | 2023-04 | 15000 | Tax & legal advice | Tax & legal advice | Cash outflow
|  |  |  | 2023-05-01 | 2023-05 | 15000 | VAT Over Sales | Sales VAT | Cash outflow
|  |  |  | 2023-06-01 | 2023-06 | 15000 | Withholding Tax | Withholding tax | Cash outflow
|  |  |  | 2023-07-01 | 2023-07 | 15000 | Withholding tax | Withholding tax | Cash outflow
|  |  |  | 2023-08-01 | 2023-08 | 15000
|  |  |  | 2023-09-01 | 2023-09 | 15000
|  |  |  | 2023-10-01 | 2023-10 | 15000
|  |  |  | 2023-11-01 | 2023-11 | 15000
|  |  |  | 2023-12-01 | 2023-12 | 15000
|  |  |  | 2024-01-01 | 2024-01 | 15000
|  |  |  | 2024-02-01 | 2024-02 | 15000
|  |  |  | 2024-03-01 | 2024-03 | 15000
|  |  |  | 2024-04-01 | 2024-04 | 15000
|  |  |  | 2024-05-01 | 2024-05 | 15000
|  |  |  | 2024-06-01 | 2024-06 | 15000
|  |  |  | 2024-07-01 | 2024-07 | 15000
|  |  |  | 2024-08-01 | 2024-08 | 15000
|  |  |  | 2024-09-01 | 2024-09 | 15000
|  |  |  | 2024-10-01 | 2024-10 | 15000
|  |  |  | 2024-11-01 | 2024-11 | 15000
|  |  |  | 2024-12-01 | 2024-12 | 15000
|  |  |  | 2025-01-01 | 2025-01 | 15000
|  |  |  | 2025-02-01 | 2025-02 | 15000
|  |  |  | 2025-03-01 | 2025-03 | 15000
|  |  |  | 2025-04-01 | 2025-04 | 15000
|  |  |  | 2025-05-01 | 2025-05 | 15000
|  |  |  | 2025-06-01 | 2025-06 | 15000
|  |  |  | 2025-07-01 | 2025-07 | 15000
|  |  |  | 2025-08-01 | 2025-08 | 15000
|  |  |  | 2025-09-01 | 2025-09 | 15000
|  |  |  | 2025-10-01 | 2025-10 | 15000
|  |  |  | 2025-11-01 | 2025-11 | 15000
|  |  |  | 2025-12-01 | 2025-12 | 15000
Formulas:
Core assumptions = DATE(YEAR([Core assumptions, row above]),MONTH([Core assumptions, row above])+1,1)
Note on B6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: legacy Info tab. Used only when a monthly FX rate is unavailable.
Note on B8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Source: legacy Info tab. Applied to the six core hard-cost categories, excluding New Infrastructure.

## Vendors
Kalindo Cove - Vendor Master | [5 empty] | ← Back to Cover
Vendor directory standardized for cost classification and cash control.
← Back to Cover
Vendor ID | Vendor | Original Role | Standard Category | Active | Notes
VEN001 | Bumi Cipta Struktur | Structure Engineer | Structure Engineer | Yes | Imported from Info tab
VEN002 | Wayan Suartika | Land Survey | Land Survey | Yes | Imported from Info tab
VEN003 | CV Lestari Tanah | Soil Test | Soil Test | Yes | Imported from Info tab
VEN004 | CV Tirta Rekayasa | Soil Test | Soil Test | Yes | Imported from Info tab
VEN005 | PPAT Wulandari | Notary | Notary | Yes | Imported from Info tab
VEN006 | SDK Interiors | Interior Designer | Interior Designer | Yes | Imported from Info tab
VEN007 | Reza P | Interior Designer | Interior Designer | Yes | Imported from Info tab
VEN008 | Meridian Tax Advisors | Tax & legal advice | Tax & legal advice | Yes | Imported from Info tab
VEN009 | Clearpoint Legal Solutions | Tax & legal advice | Tax & legal advice | Yes | Imported from Info tab
VEN010 | Dewi Santoso | Tax & legal advice | Tax & legal advice | Yes | Imported from Info tab
VEN011 | CV. Ardana Solusi Engineering | MEP Consultant | MEP Consultant | Yes | Imported from Info tab
VEN012 | BTR | Quantity Surveyor | Quantity Surveyor | Yes | Imported from Info tab
VEN013 | Nusantara Studio | Architect Cost | Architect Cost | Yes | Imported from Info tab
VEN014 | Internal reinbursment | Project Management | Project Management | Yes | Imported from Info tab
VEN015 | Java PM | Project Management | Project Management | Yes | Imported from Info tab
VEN016 | Income Tax | Income Tax | Income Tax | Yes | Imported from Info tab
VEN017 | Withholding tax | Withholding tax | Withholding tax | Yes | Imported from Info tab
VEN018 | Bank Monthly Fees | Bank Monthly Fees | Bank fees | Yes | Imported from Info tab
VEN019 | Sitegrid? | Sitegrid? | Sitegrid / Other QS | Yes | Imported from Info tab
VEN020 | Miscellaneous | Miscellaneous | Miscellaneous | Yes | Imported from Info tab
VEN021 | TBD_Interior Cost | Interior Cost | Interior Cost | Yes | Imported from Info tab
VEN022 | TBD_Preliminaries | Preliminaries | Preliminaries | Yes | Imported from Info tab
VEN023 | TBD_Structure & Architecture | Structure & Architecture | Structure & Architecture | Yes | Imported from Info tab
VEN024 | TBD_MEP | MEP | MEP | Yes | Imported from Info tab
VEN025 | TBD_Provisional Sum | Provisional Sum | Provisional Sum | Yes | Imported from Info tab
VEN026 | TBD_Landscaping | Landscaping | Landscaping | Yes | Imported from Info tab
VEN027 | TBD_Network & Infrastructure upgrade | Network & Infrastructure upgrade | Network & Infrastructure upgrade | Yes | Imported from Info tab
VEN028 | TBD_Interior Designer | Interior Designer | Interior Designer | Yes | Imported from Info tab
VEN029 | TBD_Landscape Designer | Landscape Designer | Landscape Designer | Yes | Imported from Info tab
VEN030 | TBD_Mep Engineering | Mep Engineering | MEP Engineering | Yes | Imported from Info tab
VEN031 | Contingency | Contingency | Contingency | Yes | Imported from Info tab
VEN032 | Staff | Staff | Staff | Yes | Imported from Info tab
VEN033 | Kalindo Resort A&G allocation | A&G Allocation | A&G Allocation | Yes | Imported from Info tab
VEN034 | OFFICIAL Partners New Development | Other professional fees | Other professional fees | Yes | Imported from Info tab
VEN035 | 3. Land Costs | 3. Land Costs | Land Costs | Yes | Imported from Info tab
VEN036 | 4. Income tax | 4. Income tax | Income tax | Yes | Imported from Info tab

## Bank_IDR (hidden)
Kalindo Cove - IDR Bank Feed
Raw bank statement feed. Imported values are preserved; summary checks are formula-driven.
Opening balance | 0 | Closing balance | 56809797.42 |  | Total debits | 2293666180.6 | Total credits | 2350475978.02 |  |  |  |  | ← Back to Cover
Movement check | 56809797.42 | Difference | 7.4506e-08
Account | Post Date | Effective Date | Cheque No | Description / Remarks | Debit IDR | Credit IDR | Reported Balance IDR | Transaction Code | Reference No | Internal Transfer | Net Movement | Ledger Match
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2022-12-29 13:42 | 2022-12-29 13:42 |  | BizChannel TRF FR KALINDO ADVENTURE Convert USD 10.000 to IDR | 0 | 157300000 | 157300000 | 514 | 349856ZA96789478 | Yes | 157300000 | Unmatched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2022-12-31 23:59 | 2022-12-31 23:59 |  | CREDIT INTEREST | 0 | 1862.33 | 157301862.33 | 160 | JE5658549038347 | No | 1862.33 | Unmatched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2022-12-31 23:59 | 2022-12-31 23:59 |  | WITHHOLDING TAX | 372.47 | 0 | 157301489.86 | 198 | SJ6969434941072 |  | -372.47 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-01-02 09:23 | 2023-01-02 09:23 |  | CHEQUE STAMP DUTY | 275000 | 0 | 156751489.86 | 438 | 103256JONW149012 |  | -275000 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-01-02 09:23 | 2023-01-02 09:23 |  | CHEQUE STAMP DUTY | 275000 | 0 | 157026489.86 | 438 | 583036BMNS929476 |  | -275000 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-01-02 13:39 | 2023-01-02 13:39 |  | Nusantara Studio 5 : 2nd DP Kalindo New Development BANK ARTHA 46 PT Nusantara Studio 5 05892527 832949470389618567 | 134472370 | 0 | 22279119.86 | 63 | 789436LW32321890 |  | -134472370 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-01-02 13:39 | 2023-01-02 13:39 |  | Nusantara Studio 5 : 2nd DP Kalindo New Development BANK ARTHA 46 PT Nusantara Studio 5 05892527 832949470389618567 | 2900 | 0 | 22276219.86 | 803 | 789436LW32321890 |  | -2900 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-01-18 13:58 | 2023-01-18 13:58 |  | BizChannel TRF FR KALINDO ADVENTURE Convert USD 7000 Kalindo 2.0 | 0 | 105385000 | 127661219.86 | 514 | 896181GB21674365 | Yes | 105385000 | Unmatched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-01-19 08:29 | 2023-01-19 08:29 |  | Wulandari Kusuma: DP Villa 2.0 project BANK SEJAHTERA INDONES Wulandari Kusuma Sa 018727252361234 125878943634521650 | 104462500 | 0 | 23198719.86 | 63 | 329652NI58781090 |  | -104462500 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-01-19 08:29 | 2023-01-19 08:29 |  | Wulandari Kusuma: DP Villa 2.0 project BANK SEJAHTERA INDONES Wulandari Kusuma Sa 018727252361234 125878943634521650 | 2900 | 0 | 23195819.86 | 803 | 329652NI58781090 |  | -2900 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-01-20 23:59 | 2023-01-20 23:59 |  | MONTHLY ADMIN FEE | 30000 | 0 | 23165819.86 | 480 | ON6907874141456 |  | -30000 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-01-26 14:02 | 2023-01-26 14:02 |  | BizChannel TRF FR KALINDO ADVENTURE Inhouse Transfer | 0 | 82087500 | 105253319.86 | 514 | 416147GJ49410369 | Yes | 82087500 | Unmatched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-01-27 13:42 | 2023-01-27 13:42 |  | Nusantara Studio 5: Kalindo 2.0 - BP Horizon Ridge BANK ARTHA 46 PT Nusantara Studio 5 05892527 929830747850127098 | 79730666 | 0 | 25522653.86 | 63 | 672345KL43676303 |  | -79730666 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-01-27 13:42 | 2023-01-27 13:42 |  | Nusantara Studio 5: Kalindo 2.0 - BP Horizon Ridge BANK ARTHA 46 PT Nusantara Studio 5 05892527 929830747850127098 | 2900 | 0 | 25519753.86 | 803 | 672345KL43676303 |  | -2900 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-02-20 23:59 | 2023-02-20 23:59 |  | MONTHLY ADMIN FEE | 30000 | 0 | 25489753.86 | 480 | GP0703412505290 |  | -30000 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-03-16 11:01 | 2023-03-16 11:01 |  | BizChannel TRF FR KALINDO ADVENTURE Inhouse Transfer | 0 | 154320000 | 179809753.86 | 514 | 878321ED85434149 | Yes | 154320000 | Unmatched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-03-16 11:08 | 2023-03-16 11:08 |  | Nusantara Studio 5: DP of Design Development BANK ARTHA 46 PT Nusantara Studio 5 05892527 032727252305296387 | 2900 | 0 | 35829246.86 | 803 | 341856FW98787610 |  | -2900 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-03-16 11:08 | 2023-03-16 11:08 |  | Nusantara Studio 5: DP of Design Development BANK ARTHA 46 PT Nusantara Studio 5 05892527 032727252305296387 | 143977607 | 0 | 35832146.86 | 63 | 341856FW98787610 |  | -143977607 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-03-20 23:59 | 2023-03-20 23:59 |  | MONTHLY ADMIN FEE | 30000 | 0 | 35799246.86 | 480 | QV8721290703850 |  | -30000 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-04-13 12:58 | 2023-04-13 12:58 |  | BizChannel TRF FR KALINDO ADVENTURE | 0 | 44325000 | 80124246.86 | 514 | 103692PG36943632 | Yes | 44325000 | Unmatched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-04-14 08:27 | 2023-04-14 08:27 |  | CV Ardana : Kalindo 2.0- Inv 054 055 BANK ARTHA 46 CV. Ardana Solusi E 5694967494 618767416721610587 | 41656250 | 0 | 38467996.86 | 63 | 892787WD01214341 |  | -41656250 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-04-14 08:27 | 2023-04-14 08:27 |  | CV Ardana : Kalindo 2.0- Inv 054 055 BANK ARTHA 46 CV. Ardana Solusi E 5694967494 618767416721610587 | 2900 | 0 | 38465096.86 | 803 | 892787WD01214341 |  | -2900 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-04-20 23:59 | 2023-04-20 23:59 |  | MONTHLY ADMIN FEE | 30000 | 0 | 38435096.86 | 480 | AV8309214583252 |  | -30000 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-05-20 23:59 | 2023-05-20 23:59 |  | MONTHLY ADMIN FEE | 30000 | 0 | 38405096.86 | 480 | AT8967458325678 |  | -30000 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-06-20 23:59 | 2023-06-20 23:59 |  | MONTHLY ADMIN FEE | 30000 | 0 | 38375096.86 | 480 | XW7072949658981 |  | -30000 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-06-22 14:06 | 2023-06-22 14:06 |  | BizChannel TRF FR KALINDO ADVENTURE Convert USD 80000 | 0 | 1193600000 | 1231975096.86 | 514 | 761254FU36561470 | Yes | 1193600000 | Unmatched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-06-23 08:30 | 2023-06-23 08:30 |  | Nusantara Studio 5:PR065403/JUN2023 BANK ARTHA 46 PT Nusantara Studio 5 05892527 769612167070949412 | 2900 | 0 | 292871067.86 | 803 | 369214DI58987256 |  | -2900 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-06-23 08:30 | 2023-06-23 08:30 |  | Nusantara Studio 5:PR065403/JUN2023 BANK ARTHA 46 PT Nusantara Studio 5 05892527 769612167070949412 | 939101129 | 0 | 292873967.86 | 63 | 369214DI58987256 |  | -939101129 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-06-30 23:59 | 2023-06-30 23:59 |  | WITHHOLDING TAX | 3947.15 | 0 | 292886856.47 | 198 | BG1232547056769 |  | -3947.15 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-06-30 23:59 | 2023-06-30 23:59 |  | CREDIT INTEREST | 0 | 19735.76 | 292890803.62 | 160 | ST2721036749854 | No | 19735.76 | Unmatched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-07-14 08:18 | 2023-07-14 08:18 |  | BTR: Ref.Sub/23067/GC/VI/2023 PT BANK MERIDIAN INDONE PT Bintang Trirasa 909030129654 509632703214749656 | 2900 | 0 | 102367191.47 | 803 | 274709CR41250527 |  | -2900 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-07-14 08:18 | 2023-07-14 08:18 |  | BTR: Ref.Sub/23067/GC/VI/2023 PT BANK MERIDIAN INDONE PT Bintang Trirasa 909030129654 509632703214749656 | 142138865 | 0 | 102370091.47 | 63 | 274709CR41250527 |  | -142138865 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-07-14 08:18 | 2023-07-14 08:18 |  | BTR: Ref.Sub/2306/GC/III/2023 PT BANK MERIDIAN INDONE PT Bintang Trirasa 909030129654 072969416141612381 | 2900 | 0 | 244508956.47 | 803 | 787276ZA10981018 |  | -2900 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-07-14 08:18 | 2023-07-14 08:18 |  | BTR: Ref.Sub/2306/GC/III/2023 PT BANK MERIDIAN INDONE PT Bintang Trirasa 909030129654 072969416141612381 | 48375000 | 0 | 244511856.47 | 63 | 787276ZA10981018 |  | -48375000 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-07-20 23:59 | 2023-07-20 23:59 |  | MONTHLY ADMIN FEE | 30000 | 0 | 102337191.47 | 480 | IZ2901418767878 |  | -30000 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-07-31 11:13 | 2023-07-31 11:13 |  | BizChannel TRF FR KALINDO ADVENTURE Convert USD 10000 Kalindo 2.0 | 0 | 150700000 | 253037191.47 | 514 | 876521UL01294721 | Yes | 150700000 | Unmatched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-07-31 11:14 | 2023-07-31 11:14 |  | Nusantara Studio 5: DP Architectural Kiri Amahu 3 BANK ARTHA 46 PT Nusantara Studio 5 05892527 474121690527034187 | 2900 | 0 | 93287896.47 | 803 | 030963UD01214763 |  | -2900 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-07-31 11:14 | 2023-07-31 11:14 |  | Nusantara Studio 5: DP Architectural Kiri Amahu 3 BANK ARTHA 46 PT Nusantara Studio 5 05892527 474121690527034187 | 159746395 | 0 | 93290796.47 | 63 | 030963UD01214763 |  | -159746395 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-07-31 23:59 | 2023-07-31 23:59 |  | WITHHOLDING TAX | 5603.78 | 0 | 93310311.59 | 198 | TA7292109410165 |  | -5603.78 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-07-31 23:59 | 2023-07-31 23:59 |  | CREDIT INTEREST | 0 | 28018.9 | 93315915.37 | 160 | EV8789036161834 | No | 28018.9 | Unmatched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-08-11 08:15 | 2023-08-11 08:15 |  | Java PM: Kalindo 2.0- Room Rental 1mo BMA (BANK MITRA A Ayu Kartika Le 8743412121 125616761056925210 | 2900 | 0 | 90407411.59 | 803 | 109410ZO90921436 |  | -2900 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-08-11 08:15 | 2023-08-11 08:15 |  | Java PM: Kalindo 2.0- Room Rental 1mo BMA (BANK MITRA A Ayu Kartika Le 8743412121 125616761056925210 | 2900000 | 0 | 90410311.59 | 63 | 109410ZO90921436 |  | -2900000 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-08-18 14:24 | 2023-08-18 14:24 |  | BizChannel TRF FR KALINDO ADVENTURE Convert USD 20000 Kalindo 2.0 | 0 | 305700000 | 396107411.59 | 514 | 743476RE32967898 | Yes | 305700000 | Unmatched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-08-18 14:53 | 2023-08-18 14:53 |  | Notary Wulandari: alindo 2.0- HGB Split BANK SEJAHTERA INDONES Wulandari Kusuma Sa 018727252361234 345210343092389690 | 2900 | 0 | 61104511.59 | 803 | 561412LI56523296 |  | -2900 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-08-18 14:53 | 2023-08-18 14:53 |  | Notary Wulandari: alindo 2.0- HGB Split BANK SEJAHTERA INDONES Wulandari Kusuma Sa 018727252361234 345210343092389690 | 335000000 | 0 | 61107411.59 | 63 | 561412LI56523296 |  | -335000000 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-08-20 23:59 | 2023-08-20 23:59 |  | MONTHLY ADMIN FEE | 30000 | 0 | 61074511.59 | 480 | ED4383418541816 |  | -30000 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-08-31 23:59 | 2023-08-31 23:59 |  | WITHHOLDING TAX | 1193.27 | 0 | 61079284.68 | 198 | OH0163630561878 |  | -1193.27 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-08-31 23:59 | 2023-08-31 23:59 |  | CREDIT INTEREST | 0 | 5966.36 | 61080477.95 | 160 | ZK9496565450921 | No | 5966.36 | Unmatched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-09-20 23:59 | 2023-09-20 23:59 |  | MONTHLY ADMIN FEE | 30000 | 0 | 61049284.68 | 480 | GD6521072123652 |  | -30000 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-09-21 08:14 | 2023-09-21 08:14 |  | Clearpoint: Kalindo 2.0- Inv FX23-CIAS-2021 BANK CENDANA INDONE PT Solidatama Sukse 1218947694 901018341636901836 | 2900 | 0 | 7862831.68 | 803 | 694127GP81832985 |  | -2900 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-09-21 08:14 | 2023-09-21 08:14 |  | Clearpoint: Kalindo 2.0- Inv FX23-CIAS-2021 BANK CENDANA INDONE PT Solidatama Sukse 1218947694 901018341636901836 | 53183553 | 0 | 7865731.68 | 63 | 694127GP81832985 |  | -53183553 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-10-03 08:10 | 2023-10-03 08:10 |  | Ardana Solusi: Kalindo 2.0- Inv 183/HSE/IX BANK ARTHA 46 CV. Ardana Solusi 5694967494 121690107836769830 | 2900 | 0 | 4634931.68 | 803 | 832561OD41050587 |  | -2900 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-10-03 08:10 | 2023-10-03 08:10 |  | Ardana Solusi: Kalindo 2.0- Inv 183/HSE/IX BANK ARTHA 46 CV. Ardana Solusi 5694967494 121690107836769830 | 3225000 | 0 | 4637831.68 | 63 | 832561OD41050587 |  | -3225000 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-10-13 12:36 | 2023-10-13 12:36 |  | BizChannel TRF FR KALINDO ADVENTURE Convert USD10000 to KALINDO 2.0Rp | 0 | 157000000 | 161634931.68 | 514 | 565294FC34705496 | Yes | 157000000 | Unmatched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-10-16 08:12 | 2023-10-16 08:12 |  | Ardana Solusi Eng:Inv187188 BANK ARTHA 46 CV. Ardana Solusi 5694967494 632705896547616501 | 2900 | 0 | 89123281.68 | 803 | 634921GR87230769 |  | -2900 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-10-16 08:12 | 2023-10-16 08:12 |  | Ardana Solusi Eng:Inv187188 BANK ARTHA 46 CV. Ardana Solusi 5694967494 632705896547616501 | 72508750 | 0 | 89126181.68 | 063 | 634921GR87230769 |  | -72508750 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-10-20 23:59 | 2023-10-20 23:59 |  | MONTHLY ADMIN FEE | 30000 | 0 | 89093281.68 | 480 | JE7092983416185 |  | -30000 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-10-31 23:59 | 2023-10-31 23:59 |  | WITHHOLDING TAX | 578.93 | 0 | 89095597.42 | 198 | ST8521676709036 |  | -578.93 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-10-31 23:59 | 2023-10-31 23:59 |  | CREDIT INTEREST | 0 | 2894.67 | 89096176.35 | 160 | DG7232963218529 | No | 2894.67 | Unmatched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-11-17 08:11 | 2023-11-17 08:11 |  | BTR: Inv 2 IN202300322 PT BANK MERIDIAN INDONE PT Bintang Trirasa 909030129654 163450905072947896 | 2900 | 0 | 57142697.42 | 803 | 216709MX27276367 |  | -2900 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-11-17 08:11 | 2023-11-17 08:11 |  | BTR: Inv 2 IN202300322 PT BANK MERIDIAN INDONE PT Bintang Trirasa 909030129654 163450905072947896 | 31950000 | 0 | 57145597.42 | 063 | 216709MX27276367 |  | -31950000 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-11-20 08:09 | 2023-11-20 08:09 |  | BTR: Inv 2 IN202300322 BP PT BANK MERIDIAN INDONE PT Bintang Trirasa 909030129654 345858909452745652 | 2900 | 0 | 56839797.42 | 803 | 654389YB83072989 |  | -2900 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-11-20 08:09 | 2023-11-20 08:09 |  | BTR: Inv 2 IN202300322 BP PT BANK MERIDIAN INDONE PT Bintang Trirasa 909030129654 345858909452745652 | 300000 | 0 | 56842697.42 | 63 | 654389YB83072989 |  | -300000 | Matched
Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | 2023-11-20 23:59 | 2023-11-20 23:59 |  | MONTHLY ADMIN FEE | 30000 | 0 | 56809797.42 | 480 | AT2943036107250 |  | -30000 | Matched

## Bank_USD (hidden)
Kalindo Cove - USD Bank Feed
Raw bank statement feed. Imported values are preserved; summary checks are formula-driven.
Opening balance | 0 | Closing balance | 366007.27 |  | Total debits | 389334.22 | Total credits | 755341.49 |  |  |  |  | ← Back to Cover
Movement check | 366007.27 | Difference | 0
Account | Post Date | Effective Date | Cheque No | Description / Remarks | Debit USD | Credit USD | Reported Balance USD | Transaction Code | Reference No | Internal Transfer | Net Movement | Ledger Match
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2022-12-29 13:11 | 2022-12-29 13:11 |  | BizChannel TRF FR KALINDO ADVENTURE Payment from Thomas Whitfield | 0 | 221995 | 221995 | 514 | 234907AV87236149 | No | 221995 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2022-12-29 13:42 | 2022-12-29 13:42 |  | BizChannel TRF TO KALINDO ADVENTURE Convert USD 10.000 to IDR | 10000 | 0 | 211995 | 565 | 349856ZA96789478 |  | -10000 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2022-12-31 23:59 | 2022-12-31 23:59 |  | CREDIT INTEREST | 0 | 1.79 | 211996.79 | 160 | YV6327672963098 | No | 1.79 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2022-12-31 23:59 | 2022-12-31 23:59 |  | WITHHOLDING TAX | 0.36 | 0 | 211996.43 | 198 | XU7214963670187 |  | -0.36 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-01-18 13:58 | 2023-01-18 13:58 |  | BizChannel TRF TO KALINDO ADVENTURE Convert USD 7000 Kalindo 2.0 | 7000 | 0 | 204996.43 | 565 | 896181GB21674365 |  | -7000 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-01-20 23:59 | 2023-01-20 23:59 |  | MONTHLY ADMIN FEE | 5 | 0 | 204991.43 | 480 | GF2189290945038 |  | -5 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-01-26 14:02 | 2023-01-26 14:02 |  | BizChannel TRF TO KALINDO ADVENTURE Inhouse Transfer | 5500 | 0 | 199491.43 | 565 | 416147GJ49410369 |  | -5500 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-01-31 23:59 | 2023-01-31 23:59 |  | WITHHOLDING TAX | 4.02 | 0 | 199507.51 | 198 | MH2565834981052 |  | -4.02 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-01-31 23:59 | 2023-01-31 23:59 |  | CREDIT INTEREST | 0 | 20.1 | 199511.53 | 160 | KB2381458963696 | No | 20.1 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-02-16 08:02 | 2023-02-16 08:02 |  | INCOMING SWIFT 4767278983470105 THOMAS BRADLEY WHITFIELD TTEE INV 001/KAS/KALINDO 2.0/0223 | 0 | 221995 | 421502.51 | 626 | 212945YFKP610769 | No | 221995 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-02-20 23:59 | 2023-02-20 23:59 |  | MONTHLY ADMIN FEE | 5 | 0 | 421497.51 | 480 | ID0909076389656 |  | -5 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-02-28 23:59 | 2023-02-28 23:59 |  | WITHHOLDING TAX | 5.81 | 0 | 421520.76 | 198 | ZW7498761674143 |  | -5.81 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-02-28 23:59 | 2023-02-28 23:59 |  | CREDIT INTEREST | 0 | 29.06 | 421526.57 | 160 | UH4723036709274 | No | 29.06 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-03-16 11:01 | 2023-03-16 11:01 |  | BizChannel TRF TO KALINDO ADVENTURE Inhouse Transfer | 10000 | 0 | 411520.76 | 565 | 878321ED85434149 |  | -10000 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-03-20 23:59 | 2023-03-20 23:59 |  | MONTHLY ADMIN FEE | 5 | 0 | 411515.76 | 480 | KN6125254563298 |  | -5 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-03-31 23:59 | 2023-03-31 23:59 |  | WITHHOLDING TAX | 9.33 | 0 | 411553.1 | 198 | UF4183632545876 |  | -9.33 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-03-31 23:59 | 2023-03-31 23:59 |  | CREDIT INTEREST | 0 | 46.67 | 411562.43 | 160 | RO9852169296369 | No | 46.67 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-04-13 12:58 | 2023-04-13 12:58 |  | BizChannel TRF TO KALINDO ADVENTURE | 3000 | 0 | 408553.1 | 565 | 103692PG36943632 |  | -3000 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-04-20 23:59 | 2023-04-20 23:59 |  | MONTHLY ADMIN FEE | 5 | 0 | 408548.1 | 480 | QX6965636583476 |  | -5 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-04-30 23:59 | 2023-04-30 23:59 |  | WITHHOLDING TAX | 8.87 | 0 | 408583.58 | 198 | MR8767298527636 |  | -8.87 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-04-30 23:59 | 2023-04-30 23:59 |  | CREDIT INTEREST | 0 | 44.35 | 408592.45 | 160 | LU5634981056961 | No | 44.35 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-05-20 23:59 | 2023-05-20 23:59 |  | MONTHLY ADMIN FEE | 5 | 0 | 408578.58 | 480 | LA7672123852385 |  | -5 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-05-31 23:59 | 2023-05-31 23:59 |  | WITHHOLDING TAX | 9.14 | 0 | 408615.12 | 198 | UX8585298763616 |  | -9.14 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-05-31 23:59 | 2023-05-31 23:59 |  | CREDIT INTEREST | 0 | 45.68 | 408624.26 | 160 | OR4101096561892 | No | 45.68 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-06-20 23:59 | 2023-06-20 23:59 |  | MONTHLY ADMIN FEE | 5 | 0 | 408610.12 | 480 | BG1610125476569 |  | -5 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-06-22 14:06 | 2023-06-22 14:06 |  | BizChannel TRF TO KALINDO ADVENTURE Convert USD 80000 | 80000 | 0 | 328610.12 | 565 | 761254FU36561470 |  | -80000 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-06-27 13:43 | 2023-06-27 13:43 |  | RM No: 2361670541456907496 SD Meridian INV 1161 ARCHITECTUREFEE 48 Elm Court Lane ET67ARKB07214905274543 | 26.65 | 0 | 314257.01 | 894 | 965296J456525856 |  | -26.65 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-06-27 13:43 | 2023-06-27 13:43 |  | RM No: 2361670541456907496 SD Meridian INV 1161 ARCHITECTUREFEE 48 Elm Court Lane ET67ARKB07214905274543 | 5 | 0 | 314283.66 | 803 | 965296J456525856 |  | -5 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-06-27 13:43 | 2023-06-27 13:43 |  | RM No: 2361670541456907496 SD Meridian INV 1161 ARCHITECTUREFEE 48 Elm Court Lane ET67ARKB07214905274543 | 14321.46 | 0 | 314288.66 | 89 | 965296J456525856 |  | -14321.46 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-06-30 23:59 | 2023-06-30 23:59 |  | WITHHOLDING TAX | 8.2 | 0 | 314289.83 | 198 | WF8589430103694 |  | -8.2 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-06-30 23:59 | 2023-06-30 23:59 |  | CREDIT INTEREST | 0 | 41.02 | 314298.03 | 160 | AJ2107296525634 | No | 41.02 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-07-20 23:59 | 2023-07-20 23:59 |  | MONTHLY ADMIN FEE | 5 | 0 | 314284.83 | 480 | CZ6725832381612 |  | -5 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-07-31 11:13 | 2023-07-31 11:13 |  | BizChannel TRF TO KALINDO ADVENTURE Convert USD 10000 Kalindo 2.0 | 10000 | 0 | 304284.83 | 565 | 876521UL01294721 |  | -10000 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-07-31 23:59 | 2023-07-31 23:59 |  | WITHHOLDING TAX | 6.73 | 0 | 304311.73 | 198 | NK7092121418705 |  | -6.73 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-07-31 23:59 | 2023-07-31 23:59 |  | CREDIT INTEREST | 0 | 33.63 | 304318.46 | 160 | HO9674709096129 | No | 33.63 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-08-18 14:24 | 2023-08-18 14:24 |  | BizChannel TRF TO KALINDO ADVENTURE Convert USD 20000 Kalindo 2.0 | 20000 | 0 | 284311.73 | 565 | 743476RE32967898 |  | -20000 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-08-20 23:59 | 2023-08-20 23:59 |  | MONTHLY ADMIN FEE | 5 | 0 | 284306.73 | 480 | HU3614909092385 |  | -5 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-08-31 23:59 | 2023-08-31 23:59 |  | WITHHOLDING TAX | 6.25 | 0 | 284331.73 | 198 | QV0921296387634 |  | -6.25 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-08-31 23:59 | 2023-08-31 23:59 |  | CREDIT INTEREST | 0 | 31.25 | 284337.98 | 160 | HW5672347252941 | No | 31.25 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-09-20 23:59 | 2023-09-20 23:59 |  | MONTHLY ADMIN FEE | 5 | 0 | 284326.73 | 480 | QD8367672121830 |  | -5 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-09-30 23:59 | 2023-09-30 23:59 |  | WITHHOLDING TAX | 5.78 | 0 | 284349.84 | 198 | ZW9278945812383 |  | -5.78 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-09-30 23:59 | 2023-09-30 23:59 |  | CREDIT INTEREST | 0 | 28.89 | 284355.62 | 160 | YF0543896941258 | No | 28.89 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-10-13 12:36 | 2023-10-13 12:36 |  | BizChannel TRF TO KALINDO ADVENTURE Convert USD10000 to KALINDO 2.0Rp | 10000 | 0 | 274349.84 | 565 | 565294FC34705496 |  | -10000 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-10-20 23:59 | 2023-10-20 23:59 |  | MONTHLY ADMIN FEE | 5 | 0 | 274344.84 | 480 | XI1472707818165 |  | -5 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-10-30 12:34 | 2023-10-30 12:34 |  | RM No: 0743872705294321210 SD Meridian INV 1182 1161 48 Elm Court Lane ET67ARKB07214905274543 | 25.32 | 0 | 271158.98 | 894 | 3292725878367016 |  | -25.32 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-10-30 12:34 | 2023-10-30 12:34 |  | RM No: 0743872705294321210 SD Meridian INV 1182 1161 48 Elm Court Lane ET67ARKB07214905274543 | 5 | 0 | 271184.3 | 803 | 3292725878367016 |  | -5 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-10-30 12:34 | 2023-10-30 12:34 |  | RM No: 0743872705294321210 SD Meridian INV 1182 1161 48 Elm Court Lane ET67ARKB07214905274543 | 3155.54 | 0 | 271189.3 | 089 | 3292725878367016 |  | -3155.54 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-10-31 23:59 | 2023-10-31 23:59 |  | WITHHOLDING TAX | 5.81 | 0 | 271182.22 | 198 | PA9018101056181 |  | -5.81 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-10-31 23:59 | 2023-10-31 23:59 |  | CREDIT INTEREST | 0 | 29.05 | 271188.03 | 160 | LO1812527870763 | No | 29.05 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-11-14 17:28 | 2023-11-14 17:28 |  | BizChannel TRF TO KALINDO ADVENTURE Inhouse Transfer | 216169.95 | 0 | 55012.27 | 565 | 096749WR21632747 |  | -216169.95 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-11-20 23:59 | 2023-11-20 23:59 |  | MONTHLY ADMIN FEE | 5 | 0 | 55007.27 | 480 | JW9290989456127 |  | -5 | Matched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-11-21 08:08 | 2023-11-21 08:08 |  | INCOMING SWIFT K3210305 767 9 ISABELLA MARIE CONTI PAID AS SHAREHOLDER OF PT CONTI PRIMA | 0 | 156000.5 | 211007.77 | 626 | 189836XIVE785250 | No | 156000.5 | Unmatched
Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 2023-11-22 11:28 | 2023-11-22 11:28 |  | INCOMING SWIFT 4385630501672549 KADEK LARASATI DEWI S.HM.KN. /INV/DP PEMBELIAN TANAH | 0 | 154999.5 | 366007.27 | 626 | 143652NQXG385870 | No | 154999.5 | Unmatched

## Outflows
Kalindo Cove - Outflow Ledger
Transaction-level actual outflows translated at monthly average FX and reconciled to bank references.
Actual paid through cut-off
| 788238.5499 | Unmapped USD | 0 | Unmatched bank rows | 0 | [7 empty] | ← Back to Cover
Txn ID | Date | Bank / Account | Source | Reference No | Vendor | Original Type | Standard Category | Villa Tag | Amount IDR | FX IDR / USD | Amount USD | Period | Bank Status | Budget Flag | Description / Note | Source Row
OUT-0001 | 2022-02-10 | Other | Sari | OPEX IDR-100222 | Nusantara Studio | Architect Common cost | Architect Cost | Common | 107625000 | 14371 | 7489.0404 | 2022-02-01 | Manual | Budgeted | Kalindo 2.0-Nusantara Studio : Architectural fee of Palm Valley Kirana Hai & Horizon Ridge Kalindo | 2
OUT-0002 | 2022-04-28 | Other | Sari | OPEX IDR-280422 | Nusantara Studio | Architect Common cost | Architect Cost | Common | 36000000 | 14418 | 2496.8789 | 2022-04-01 | Manual | Budgeted | Kalindo 2.0-Nusantara Studio : Additional works for Kirana Hai & Horizon Ridge Villa Project - Creating 3D Models for selected furnitures images & video adjustment & furniture placement | 3
OUT-0003 | 2022-05-20 | Other | Sari | OPEX IDR-200522 | Nusantara Studio | Architect Common cost | Architect Cost | Common | 109875000 | 14544 | 7554.6617 | 2022-05-01 | Manual | Budgeted | Kalindo 2.0-Nusantara Studio : DP architectural services Kalindo New Dev Project (Villas Former Cove) | 4
OUT-0004 | 2022-06-02 | Other | Sari | OPEX IDR-020622 | Nusantara Studio | Architect Common cost | Architect Cost | Common | 7275000 | 14848 | 489.965 | 2022-06-01 | Manual | Budgeted | Kalindo 2.0-Nusantara Studio : Additional fee for the revision interior for 2 stable villas at Palm Valley Kirana Hai & Horizon Ridge Kalindo $ 500 | 5
OUT-0005 | 2022-06-28 | Other | Sari | OPEX IDR-280622 | Nusantara Studio | Architect Common cost | Architect Cost | Common | 461839500 | 14848 | 31104.4922 | 2022-06-01 | Manual | Budgeted | Kalindo 2.0-Nusantara Studio : 2nd DP architectural services Kalindo New Dev for Villa on the Cove & Canopy House project at $ 31,851 (from total : $ 131,170, 1st DP : $ 7,500) | 6
OUT-0006 | 2022-07-14 | Other | Sari | OPEX IDR-140722 | Internal reinbursment | Project Management Costs | Project Management | Common | 74000 | 14958 | 4.9472 | 2022-07-01 | Manual | Budgeted | KALINDO 2.0 -Nadia : Exp Claim : Taxi from Office to Nusantara Studio Office | 7
OUT-0007 | 2022-09-03 | Other | Sari | OPEX IDR-030922 | Meridian Tax Advisors | Tax & legal advice | Tax & legal advice | Common | 9000000 | 15247 | 590.2801 | 2022-09-01 | Manual | Budgeted | Kalindo 2.0-Meridian : New villa project - 60% drafting reservation agreement USD 605.90 | 8
OUT-0008 | 2022-09-03 | Other | Sari | OPEX IDR-030922 | Meridian Tax Advisors | Tax & legal advice | Tax & legal advice | Common | 14854000 | 15247 | 974.2244 | 2022-09-01 | Manual | Budgeted | Kalindo 2.0-Meridian : New villa project - deposit for the review work USD 1,000 | 9
OUT-0009 | 2022-10-29 | Other | Sari | OPEX IDR-291022 | Nusantara Studio | Architect Cost | Architect Cost | Common | 85388450 | 15542 | 5494.0452 | 2022-10-01 | Manual | Budgeted | Kalindo 2.0-Nusantara Studio : 50%DP architectural services for Horizon Ridge | 10
OUT-0010 | 2022-10-31 | Other | Sari | 1022-Adjustment | Dewi Santoso | Tax & legal advice | Tax & legal advice | Common | 15000000 | 15542 | 965.1268 | 2022-10-01 | Manual | Budgeted | Kalindo 2.0-Santoso & Partners : tax opinion on Development Kalindo | 11
OUT-0011 | 2022-11-07 | Other | Sari | OPEX IDR-071122 | Nusantara Studio | Architect Cost | Architect Cost | Common | 41613428.25 | 15737 | 2644.305 | 2022-11-01 | Manual | Budgeted | Kalindo 2.0-Nusantara Studio : 50%DP IMB Drawing Villa at the Meadow | 12
OUT-0012 | 2022-11-07 | Other | Sari | OPEX IDR-071122 | Nusantara Studio | Architect Cost | Architect Cost | Common | 20806714.125 | 15737 | 1322.1525 | 2022-11-01 | Manual | Budgeted | Kalindo 2.0-Nusantara Studio : 25%DP Copied IMB Drawing Villa at the Meadow | 13
OUT-0013 | 2022-11-07 | Other | Sari | OPEX IDR-071122 | Nusantara Studio | Architect Cost | Architect Cost | Common | 29887665.75 | 15737 | 1899.1972 | 2022-11-01 | Manual | Budgeted | Kalindo 2.0-Nusantara Studio : 50%DP IMB Drawing Canopy House | 14
OUT-0014 | 2022-11-07 | Other | Sari | OPEX IDR-071122 | Nusantara Studio | Architect Cost | Architect Cost | Common | 49395891.87 | 15737 | 3138.8379 | 2022-11-01 | Manual | Budgeted | Kalindo 2.0-Nusantara Studio : 50%DP IMB Drawing 3Bedroom on Slope | 15
OUT-0015 | 2022-11-07 | Other | Sari | OPEX IDR-071122 | Bumi Cipta Struktur | Structure Engineer | Structure Engineer | Common | 22200000 | 15737 | 1410.6882 | 2022-11-01 | Manual | Budgeted | Kalindo 2.0-Bumi Cipta Struktur : 30%DP IMB Drawing Horizon Ridge Top Villa | 16
OUT-0016 | 2022-11-30 | Other | Sari | OPEX IDR-301122 | Sitegrid? | Sitegrid? | Sitegrid / Other QS | Common | 24000000 | 15737 | 1525.0683 | 2022-11-01 | Manual | Budgeted | Kalindo 2.0-Sitegrid : Stage 2 bill of quantity calculation & documentation (Lot 3 Villa D) | 17
OUT-0017 | 2022-11-30 | Other | Sari | OPEX IDR-301122 | Sitegrid? | Sitegrid? | Sitegrid / Other QS | Common | 18610000 | 15737 | 1182.5634 | 2022-11-01 | Manual | Budgeted | Kalindo 2.0-Sitegrid : Stage 3 bill of quantity calculation & documentation (Lot 3 Villa D) | 18
OUT-0018 | 2022-11-30 | Other | Sari | OPEX IDR-301122 | Bumi Cipta Struktur | Structure Engineer | Structure Engineer | Common | 18000000 | 15737 | 1143.8012 | 2022-11-01 | Manual | Budgeted | Kalindo 2.0-Bumi Cipta Struktur : 30%DP structure engineer Garden Villa | 19
OUT-0019 | 2022-11-30 | Other | Sari | OPEX IDR-301122 | Bumi Cipta Struktur | Structure Engineer | Structure Engineer | Common | 13500000 | 15737 | 857.8509 | 2022-11-01 | Manual | Budgeted | Kalindo 2.0-Bumi Cipta Struktur : 30%DP structure engineer Canopy House | 20
OUT-0020 | 2022-11-30 | Other | Sari | OPEX IDR-301122 | Bumi Cipta Struktur | Structure Engineer | Structure Engineer | Common | 13500000 | 15737 | 857.8509 | 2022-11-01 | Manual | Budgeted | Kalindo 2.0-Bumi Cipta Struktur : 30%DP structure engineer Hill Side Villa | 21
OUT-0021 | 2022-12-08 | Other | Sari | OPEX IDR-081222 | Nusantara Studio | Architect Cost | Architect Cost | Common | 26140500 | 15731 | 1661.7189 | 2022-12-01 | Manual | Budgeted | Kalindo 2.0-Nusantara Studio : architectural services of sorting boundaries at Kalindo New Dev + PPN (USD 1.665) | 22
OUT-0022 | 2022-12-13 | Other | Sari | OPEX IDR-131222 | Nusantara Studio | Architect Cost | Architect Cost | Common | 67381495.5 | 15731 | 4283.3574 | 2022-12-01 | Manual | Budgeted | Kalindo 2.0-Nusantara Studio : 50%DP IMB Kirana Hai Villa B (E2) | 23
OUT-0023 | 2022-12-13 | Other | Sari | OPEX IDR-131222 | Nusantara Studio | Architect Cost | Architect Cost | Common | 103525093.5 | 15731 | 6580.9607 | 2022-12-01 | Manual | Budgeted | Kalindo 2.0-Nusantara Studio : 50%DP IMB Kirana Hai Villa C (E3) | 24
OUT-0024 | 2022-12-15 | Other | Sari | GC 151222-01 | Miscellaneous | Miscellaneous | Miscellaneous | Common | 2080000 | 15731 | 132.223 | 2022-12-01 | Manual | Budgeted | Kalindo 2.0-DW surveyer for clear area stable + cutting trees | 25
OUT-0025 | 2022-12-15 | Other | Sari | GC 151222-01 | Miscellaneous | Miscellaneous | Miscellaneous | Common | 2500000 | 15731 | 158.9219 | 2022-12-01 | Manual | Budgeted | Kalindo 2.0-Chainsaw mechine for cutting trees at palm area | 26
OUT-0026 | 2022-12-15 | Other | Sari | GC 151222-01 | Miscellaneous | Miscellaneous | Miscellaneous | Common | 100000 | 15731 | 6.3569 | 2022-12-01 | Manual | Budgeted | Kalindo 2.0-Oli T2 + Bensin for land surveyer at stable | 27
OUT-0027 | 2022-12-15 | Other | Sari | OPEX IDR-151222 | Bumi Cipta Struktur | Structure Engineer | Structure Engineer | Common | 22200000 | 15731 | 1411.2262 | 2022-12-01 | Manual | Budgeted | Kalindo 2.0-Bumi Cipta : 30%DP Drawing - Villa E2 Kirana Hai | 28
OUT-0028 | 2022-12-15 | Other | Sari | OPEX IDR-151222 | Bumi Cipta Struktur | Structure Engineer | Structure Engineer | Common | 26400000 | 15731 | 1678.215 | 2022-12-01 | Manual | Budgeted | Kalindo 2.0-Bumi Cipta : 30%DP Drawing - Villa E3 Kirana Hai | 29
OUT-0029 | 2022-12-24 | Other | Sari | GC 241222-01 | Miscellaneous | Miscellaneous | Miscellaneous | Common | 60000 | 15731 | 3.8141 | 2022-12-01 | Manual | Budgeted | Kalindo 2.0-Tati Rahayu for Land surveyer | 30
OUT-0030 | 2022-12-31 23:59 | Kalindo 2.0 | Cash Movements | SJ6969434941072 | Withholding tax | Withholding Tax | Withholding tax | Common | 372.47 | 15731 | 0.023677 | 2022-12-01 | Matched | Unflagged |  | 31
OUT-0031 | 2023-01-01 | Internal Allocation | Internal Allocation |  | Kalindo Resort A&G allocation | A&G Allocation | A&G Allocation | Common | 411922500 | 14979 | 27500 | 2023-01-01 | Manual | Unflagged | Jan 2023 A&G Allocation | 32
OUT-0032 | 2023-01-02 | Kalindo 2.0 | Sari | KALINDO 2.0 IDR-020 | Nusantara Studio | Architect Cost | Architect Cost | Common | 20873150 | 14979 | 1393.4942 | 2023-01-01 | Manual | Budgeted | Kalindo 2.0-Nusantara Studio 5 : 2nd payment (25%) Copied IMB | 33
OUT-0033 | 2023-01-02 | Kalindo 2.0 | Sari | KALINDO 2.0 IDR-020 | Nusantara Studio | Architect Cost | Architect Cost | Common | 49553661 | 14979 | 3308.2089 | 2023-01-01 | Manual | Budgeted | Kalindo 2.0-Nusantara Studio 5 : 50%BP IMB Drawing 3 Bedroom S | 34
OUT-0034 | 2023-01-02 | Kalindo 2.0 | Sari | KALINDO 2.0 IDR-020 | Nusantara Studio | Architect Cost | Architect Cost | Common | 29983232 | 14979 | 2001.6845 | 2023-01-01 | Manual | Budgeted | Kalindo 2.0-Nusantara Studio 5 : 50%BP IMB Drawing Canopy House | 35
OUT-0035 | 2023-01-02 | Kalindo 2.0 | Sari | KALINDO 2.0 IDR-020 | Nusantara Studio | Architect Cost | Architect Cost | Common | 41746457 | 14979 | 2786.9989 | 2023-01-01 | Manual | Budgeted | Kalindo 2.0-Nusantara Studio 5 : 50%BP IMB Drawing Villa at Nu | 36
OUT-0036 | 2023-01-02 | Other | Sari | OPEX IDR-020123 | Internal reinbursment | Project Management Costs | Project Management | Common | 85500 | 14979 | 5.708 | 2023-01-01 | Manual | Budgeted | Kalindo 2.0-Nadia : Exp claim - Taxi from Airport to H | 37
OUT-0037 | 2023-01-02 | Other | Sari | OPEX IDR-020123 | Internal reinbursment | Project Management Costs | Project Management | Common | 70000 | 14979 | 4.6732 | 2023-01-01 | Manual | Budgeted | Kalindo 2.0-Nadia : Exp claim - Taxi from Home to Airp | 38
OUT-0038 | 2023-01-02 | Other | Sari | OPEX IDR-020123 | Internal reinbursment | Project Management Costs | Project Management | Common | 77500 | 14979 | 5.1739 | 2023-01-01 | Manual | Budgeted | Kalindo 2.0-Nadia : Exp claim - Taxi from Home to Airp | 39
OUT-0039 | 2023-01-02 09:23 | Kalindo 2.0 | Cash Movements | 103256JONW149012 | CHEQUE STAMP DUTY | Miscellaneous | Miscellaneous | Common | 275000 | 14979 | 18.359 | 2023-01-01 | Matched | Unflagged |  | 40
OUT-0040 | 2023-01-02 09:23 | Kalindo 2.0 | Cash Movements | 583036BMNS929476 | CHEQUE STAMP DUTY | Miscellaneous | Miscellaneous | Common | 275000 | 14979 | 18.359 | 2023-01-01 | Matched | Unflagged |  | 41
OUT-0041 | 2023-01-02 13:39 | Kalindo 2.0 | Cash Movements | 789436LW32321890 | Nusantara Studio | Architect Cost | Architect Cost | Common | 134472370 | 14979 | 8977.393 | 2023-01-01 | Matched | Unflagged | Nusantara Studio 5 : 2nd DP Kalindo New Development BANK ARTHA 46 PT Nusantara Studio 5 05892527 832949470389618567 | 42
OUT-0042 | 2023-01-02 13:39 | Kalindo 2.0 | Cash Movements | 789436LW32321890 | Nusantara Studio | Architect Cost | Architect Cost | Common | 2900 | 14979 | 0.1936 | 2023-01-01 | Matched | Unflagged | Nusantara Studio 5 : 2nd DP Kalindo New Development BANK ARTHA 46 PT Nusantara Studio 5 05892527 832949470389618567 | 43
OUT-0043 | 2023-01-19 08:29 | Kalindo 2.0 | Cash Movements | 329652NI58781090 | PPAT Wulandari | Notary | Notary | Common | 104462500 | 14979 | 6973.9302 | 2023-01-01 | Matched | Budgeted | Kalindo 2.0-Notary Wulandari Samapathy: Kalindo 2.0 - Cost Estimation | 44
OUT-0044 | 2023-01-19 08:29 | Kalindo 2.0 | Cash Movements | 329652NI58781090 | PPAT Wulandari | Notary | Notary | Common | 2900 | 14979 | 0.1936 | 2023-01-01 | Matched | Unflagged |  | 45
OUT-0045 | 2023-01-20 23:59 | Kalindo 2.0 | Cash Movements | ON6907874141456 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 30000 | 14979 | 2.0028 | 2023-01-01 | Matched | Unflagged |  | 46
OUT-0046 | 2023-01-20 23:59 | Kalindo 2.0 | Cash Movements | GF2189290945038 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 74895 | 14979 | 5 | 2023-01-01 | Matched | Unflagged |  | 47
OUT-0047 | 2023-01-27 | Kalindo 2.0 | Sari | KALINDO 2.0 IDR-270 | Nusantara Studio | Architect Cost | Architect Cost | Common | 84286700 | 14979 | 5626.9911 | 2023-01-01 | Manual | Budgeted | Kalindo 2.0-Nusantara Studio 5 : 50%BP architectural services | 48
OUT-0048 | 2023-01-27 13:42 | Kalindo 2.0 | Cash Movements | 672345KL43676303 | Nusantara Studio | Architect Cost | Architect Cost | Common | 79730666 | 14979 | 5322.8297 | 2023-01-01 | Matched | Unflagged | Nusantara Studio 5: Kalindo 2.0 - BP Horizon Ridge BANK ARTHA 46 PT Nusantara Studio 5 05892527 929830747850127098 | 49
OUT-0049 | 2023-01-27 13:42 | Kalindo 2.0 | Cash Movements | 672345KL43676303 | Nusantara Studio | Architect Cost | Architect Cost | Common | 2900 | 14979 | 0.1936 | 2023-01-01 | Matched | Unflagged | Nusantara Studio 5: Kalindo 2.0 - BP Horizon Ridge BANK ARTHA 46 PT Nusantara Studio 5 05892527 929830747850127098 | 50
OUT-0050 | 2023-01-31 23:59 | Kalindo 2.0 | Cash Movements | MH2565834981052 | Withholding tax | Withholding Tax | Withholding tax | Common | 60215.58 | 14979 | 4.02 | 2023-01-01 | Matched | Unflagged |  | 51
OUT-0051 | 2023-02-01 | Internal Allocation | Internal Allocation |  | Kalindo Resort A&G allocation | A&G Allocation | A&G Allocation | Common | 420035000 | 15274 | 27500 | 2023-02-01 | Manual | Unflagged | Feb 2023 A&G Allocation | 52
OUT-0052 | 2023-02-20 23:59 | Kalindo 2.0 | Cash Movements | GP0703412505290 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 30000 | 15274 | 1.9641 | 2023-02-01 | Matched | Unflagged |  | 53
OUT-0053 | 2023-02-20 23:59 | Kalindo 2.0 | Cash Movements | ID0909076389656 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 76370 | 15274 | 5 | 2023-02-01 | Matched | Unflagged |  | 54
OUT-0054 | 2023-02-24 | Other | Sari | OPEX-IDR 240223 | Bumi Cipta Struktur | Structure Engineer | Structure Engineer | Common | 18000000 | 15274 | 1178.4732 | 2023-02-01 | Manual | Budgeted | Kalindo 2.0-Bumi Cipta Struktur, CV (Wayan Sujana) : Inv II DP Inv 30% DP IMB Drawing for 2.5 BR Meadow Villa | 55
OUT-0055 | 2023-02-24 | Other | Sari | OPEX-IDR 240223 | Bumi Cipta Struktur | Structure Engineer | Structure Engineer | Common | 13500000 | 15274 | 883.8549 | 2023-02-01 | Manual | Budgeted | Kalindo 2.0-Bumi Cipta Struktur, CV (Wayan Sujana) : Inv II DP Inv 30% DP IMB Drawing for 3 BR Horizon Ridge Villa | 56
OUT-0056 | 2023-02-24 | Other | Sari | OPEX-IDR 240223 | Bumi Cipta Struktur | Structure Engineer | Structure Engineer | Common | 22200000 | 15274 | 1453.4503 | 2023-02-01 | Manual | Budgeted | Kalindo 2.0-Bumi Cipta Struktur, CV (Wayan Sujana) : Inv II DP Inv 30% DP IMB Drawing for 4 BR Horizon Ridge Top Villa | 57
OUT-0057 | 2023-02-24 | Other | Sari | OPEX-IDR 240223 | Bumi Cipta Struktur | Structure Engineer | Structure Engineer | Common | 13500000 | 15274 | 883.8549 | 2023-02-01 | Manual | Budgeted | Kalindo 2.0-Bumi Cipta Struktur, CV (Wayan Sujana) : Inv II DP Inv 30% DP IMB Drawing for 4 BR Canopy House | 58
OUT-0058 | 2023-02-28 | Other | Sari | AR Adj-280223 | Miscellaneous | Miscellaneous | Miscellaneous | Common | 3265847 | 15274 | 213.8174 | 2023-02-01 | Manual | Budgeted | Kalindo 2.0-Folio 35433 - IDR-Resort Credit-Andrew Fenwick | 59
OUT-0059 | 2023-02-28 | Other | Sari | OPEX-IDR 280223 | PPAT Wulandari | Notary | Notary | Common | 3000000 | 15274 | 196.4122 | 2023-02-01 | Manual | Budgeted | Kalindo 2.0-Notary Wulandari Samapathy : Extra Expense for 8 HGB Split of PT KAS | 60
OUT-0060 | 2023-02-28 | Other | Sari | OPEX-IDR 280223 | CV Tirta Rekayasa | Soil Test | Soil Test | Common | 185103600 | 15274 | 12118.8687 | 2023-02-01 | Manual | Budgeted | Kalindo 2.0-CV Tirta Rekayasa : Inv 40% DP of Soil Test - Geotechnic Area | 61
OUT-0061 | 2023-02-28 23:59 | Kalindo 2.0 | Cash Movements | ZW7498761674143 | Withholding tax | Withholding Tax | Withholding tax | Common | 88741.94 | 15274 | 5.81 | 2023-02-01 | Matched | Unflagged |  | 62
OUT-0062 | 2023-03-01 | Internal Allocation | Internal Allocation |  | Kalindo Resort A&G allocation | A&G Allocation | A&G Allocation | Common | 414205000 | 15062 | 27500 | 2023-03-01 | Manual | Unflagged | Mar 2023 A&G Allocation | 63
OUT-0063 | 2023-03-06 | Other | Sari | OPEX-921638303694503234 | Nusantara Studio | Architect Cost | Architect Cost | Common | 186395895 | 15062 | 12375.242 | 2023-03-01 | Manual | Unflagged | Re Return transfer invoice (IMB Kirana Hai at Kalindo 2.0 for Villa B(E2) & C(E3)) Received at 21/02/23 | 64
OUT-0064 | 2023-03-06 | Other | Sari | OPEX-921638303694503234 | Nusantara Studio | Architect Cost | Architect Cost | Common | 22504627 | 15062 | 1494.1327 | 2023-03-01 | Manual | Unflagged | Re PPN Oct Nov 22 (IMB Kirana Hai at Kalindo 2.0 for Villa B(E2) & C(E3)) Received at 21/02/23 | 65
OUT-0065 | 2023-03-13 | Other | Sari | OPEX-921638303694503234 | Internal reinbursment | Project Management Costs | Project Management | Common | 81000 | 15062 | 5.3778 | 2023-03-01 | Manual | Budgeted | Kalindo 2.0- Exp Claim - Taxi from home to airport (Fam trip) | 66
OUT-0066 | 2023-03-13 | Other | Sari | OPEX-921638303694503234 | Internal reinbursment | Project Management Costs | Project Management | Common | 96500 | 15062 | 6.4069 | 2023-03-01 | Manual | Budgeted | Kalindo 2.0- Exp Claim - Taxi from airport to home (Fam trip) | 67
OUT-0067 | 2023-03-13 | Other | Sari | OPEX-921638303694503234 | Internal reinbursment | Project Management Costs | Project Management | Common | 147400 | 15062 | 9.7862 | 2023-03-01 | Manual | Budgeted | Kalindo 2.0- Exp Claim - Lunch w/ Andrew Fenwick The Official | 68
OUT-0068 | 2023-03-16 | Kalindo 2.0 | Sari | OPEX-076507490701652901 | Nusantara Studio | Architect Cost | Architect Cost | Common | 105218100 | 15062 | 6985.6659 | 2023-03-01 | Manual | Budgeted | Kalindo 2.0- BP architectural services IMB Stable for Villa B (E2) + VAT (USD 6,877 x 15,300) | 69
OUT-0069 | 2023-03-16 | Kalindo 2.0 | Sari | OPEX-076507490701652901 | Nusantara Studio | Architect Cost | Architect Cost | Common | -5687469 | 15062 | -377.6038 | 2023-03-01 | Manual | Unflagged | Kalindo 2.0- PPh 4(2) - BP architectural services of IMB Stable for Villa B (E2) (6% x 94,791,150) | 70
OUT-0070 | 2023-03-16 | Kalindo 2.0 | Sari | OPEX-076507490701652901 | Nusantara Studio | Architect Cost | Architect Cost | Common | 100887400 | 15062 | 6698.141 | 2023-03-01 | Manual | Budgeted | Kalindo 2.0- 50% BP architectural services IMB Stable for Villa B (E3) + VAT (USD 6,593.95 x 15,300) | 71
OUT-0071 | 2023-03-16 | Kalindo 2.0 | Sari | OPEX-076507490701652901 | Nusantara Studio | Architect Cost | Architect Cost | Common | -5453379 | 15062 | -362.0621 | 2023-03-01 | Manual | Unflagged | Kalindo 2.0- PPh 4(2) - BP architectural services of IMB Stable for Villa B (E2) (6% x 90,889,650) | 72
OUT-0072 | 2023-03-16 | Kalindo 2.0 | Sari | OPEX-076507490701652901 | Nusantara Studio | Architect Cost | Architect Cost | Common | -22504627 | 15062 | -1494.1327 | 2023-03-01 | Manual | Unflagged | Over payment (IMB Kirana Hai at Kalindo 2.0 for Villa (E2) & (E3)) | 73
OUT-0073 | 2023-03-16 | Kalindo 2.0 | Sari | OPEX-032727252305296387 | Nusantara Studio | Architect Cost | Architect Cost | Common | 152204900 | 15062 | 10105.2251 | 2023-03-01 | Manual | Budgeted | Kalindo 2.0- 50% DP of Architectural service for Design Development Horizon Ridge project (from total USD 17,866) + VAT (USD 9,915.63 x 15,350) | 74
OUT-0074 | 2023-03-16 | Kalindo 2.0 | Sari | OPEX-032727252305296387 | Nusantara Studio | Architect Cost | Architect Cost | Common | -8227293 | 15062 | -546.2285 | 2023-03-01 | Manual | Unflagged | Kalindo 2.0- PPh 4(2) - 50% DP of Architectural service for Design Development Horizon Ridge project (6% x 137,121,550) | 75
OUT-0075 | 2023-03-16 11:08 | Kalindo 2.0 | Cash Movements | 341856FW98787610 | Nusantara Studio | Architect Cost | Architect Cost | Common | 2900 | 15062 | 0.19254 | 2023-03-01 | Matched | Unflagged | Nusantara Studio 5: DP of Design Development BANK ARTHA 46 PT Nusantara Studio 5 05892527 032727252305296387 | 76
OUT-0076 | 2023-03-16 11:08 | Kalindo 2.0 | Cash Movements | 341856FW98787610 | Nusantara Studio | Architect Cost | Architect Cost | Common | 143977607 | 15062 | 9558.9966 | 2023-03-01 | Matched | Unflagged | Nusantara Studio 5: DP of Design Development BANK ARTHA 46 PT Nusantara Studio 5 05892527 032727252305296387 | 77
OUT-0077 | 2023-03-20 23:59 | Kalindo 2.0 | Cash Movements | QV8721290703850 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 30000 | 15062 | 1.9918 | 2023-03-01 | Matched | Unflagged |  | 78
OUT-0078 | 2023-03-20 23:59 | Kalindo 2.0 | Cash Movements | KN6125254563298 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 75310 | 15062 | 5 | 2023-03-01 | Matched | Unflagged |  | 79
OUT-0079 | 2023-03-28 | Other | Sari | OPEX-manual transfer | SDK Interiors | Marketing & Sales | Interior Designer | Common | 103222264.2105 | 15062 | 6853.1579 | 2023-03-01 | Manual | Budgeted | Kalindo 2.0- 50%DP Inv 1138 The Phase I mobilitasation fee FF&E schedules for 5 villas (E2,E3,2BR Horizon Ridge Estate, Horizon Ridge Top, Meadow 2.5 BR Villa) | 80
OUT-0080 | 2023-03-28 | Other | Sari | OPEX-manual transfer | SDK Interiors | Marketing & Sales | Interior Designer | Common | 267552251.5263 | 15062 | 17763.3947 | 2023-03-01 | Manual | Budgeted | Kalindo 2.0- 50%DP Inv 1139 The Phase II for CGI Render 12 pcs & Vignette 6 pcs | 81
OUT-0081 | 2023-03-30 | Other | Sari | OPEX-303874327898543638 | VAT Over Sales | VAT Over Sales | Sales VAT | Common | 661328000 | 15062 | 43907.0509 | 2023-03-01 | Manual | Unflagged | Kalindo 2.0- PPN of advance payment for the sale of land located at a beachfront land plot on a remote eastern Indonesian island | 82
OUT-0082 | 2023-04-01 | Internal Allocation | Internal Allocation |  | Kalindo Resort A&G allocation | A&G Allocation | A&G Allocation | Common | 412500000 | 15000 | 27500 | 2023-04-01 | Manual | Unflagged | Apr 2023 A&G Allocation | 83
OUT-0083 | 2023-04-14 08:27 | Kalindo 2.0 | Cash Movements | 892787WD01214341 | CV. Ardana Solusi Engineering | MEP Consultant | MEP Consultant | Common | 41656250 | 15000 | 2777.0833 | 2023-04-01 | Matched | Budgeted |  | 84
OUT-0084 | 2023-04-14 08:27 | Kalindo 2.0 | Cash Movements | 892787WD01214341 | CV. Ardana Solusi Engineering | MEP Consultant | MEP Consultant | Common | 2900 | 15000 | 0.19333 | 2023-04-01 | Matched | Budgeted |  | 85
OUT-0085 | 2023-04-18 | Other | Sari | OPEX-969470969070169498 | Bumi Cipta Struktur | Structure Engineer | Structure Engineer | Common | 22200000 | 15000 | 1480 | 2023-04-01 | Manual | Budgeted | Kalindo 2.0- Inv II 30% DP IMB Document for Villa E2 Kirana Hai | 86
OUT-0086 | 2023-04-18 | Other | Sari | OPEX-969470969070169498 | Bumi Cipta Struktur | Structure Engineer | Structure Engineer | Common | 26400000 | 15000 | 1760 | 2023-04-01 | Manual | Budgeted | Kalindo 2.0- Inv II 30% DP IMB Document for Villa E3 Kirana Hai | 87
OUT-0087 | 2023-04-20 23:59 | Kalindo 2.0 | Cash Movements | AV8309214583252 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 30000 | 15000 | 2 | 2023-04-01 | Matched | Unflagged |  | 88
OUT-0088 | 2023-04-20 23:59 | Kalindo 2.0 | Cash Movements | QX6965636583476 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 75000 | 15000 | 5 | 2023-04-01 | Matched | Unflagged |  | 89
OUT-0089 | 2023-04-30 23:59 | Kalindo 2.0 | Cash Movements | MR8767298527636 | Withholding tax | Withholding Tax | Withholding tax | Common | 133050 | 15000 | 8.87 | 2023-04-01 | Matched | Unflagged |  | 90
OUT-0090 | 2023-05-01 | Internal Allocation | Internal Allocation |  | Kalindo Resort A&G allocation | A&G Allocation | A&G Allocation | Common | 412500000 | 15000 | 27500 | 2023-05-01 | Manual | Unflagged | May 2023 A&G Allocation | 91
OUT-0091 | 2023-05-03 | Other | Sari & Yudi | OPEX IDR-030523 | Clearpoint Legal Solutions | Tax & legal advice | Tax & legal advice | Common | 53428375 | 15000 | 3561.8917 | 2023-05-01 | Manual | Budgeted |  | 92
OUT-0092 | 2023-05-15 | Other | Sari | OPEX-manual transfer | SDK Interiors | Marketing & Sales | Interior Designer | Common | 78126000 | 15000 | 5208.4 | 2023-05-01 | Manual | Budgeted | Kalindo 2.0- Inv 1155 - 50%BP Phase 1 Mobilisation fee FF&E schedules for 5 villas (E2,E3,2BR Horizon Ridge Estate, Horizon Ridge Top, Meadow 2.5 BR Villa) | 93
OUT-0093 | 2023-05-15 | Other | Sari | OPEX-manual transfer | SDK Interiors | Marketing & Sales | Interior Designer | Common | 31250400 | 15000 | 2083.36 | 2023-05-01 | Manual | Budgeted | Kalindo 2.0- Inv 1155 - Additional FF&E schedules for 1 villa | 94
OUT-0094 | 2023-05-20 23:59 | Kalindo 2.0 | Cash Movements | AT8967458325678 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 30000 | 15000 | 2 | 2023-05-01 | Matched | Unflagged |  | 95
OUT-0095 | 2023-05-20 23:59 | Kalindo 2.0 | Cash Movements | LA7672123852385 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 75000 | 15000 | 5 | 2023-05-01 | Matched | Unflagged |  | 96
OUT-0096 | 2023-05-31 23:59 | Kalindo 2.0 | Cash Movements | UX8585298763616 | Withholding tax | Withholding Tax | Withholding tax | Common | 137100 | 15000 | 9.14 | 2023-05-01 | Matched | Unflagged |  | 97
OUT-0097 | 2023-06-01 | Internal Allocation | Internal Allocation |  | Kalindo Resort A&G allocation | A&G Allocation | A&G Allocation | Common | 412500000 | 15000 | 27500 | 2023-06-01 | Manual | Unflagged | Jun 2023 A&G Allocation | 98
OUT-0098 | 2023-06-15 | Other | Sari | OPEX- 921438761454929636 | Wayan Suartika | Land Survey | Land Survey | Common | 4100000 | 15000 | 273.3333 | 2023-06-01 | Manual | Budgeted | Kalindo 2.0- Additional setting out for Subdivision palm E2, E3, Horizon Ridge Top & Canopy House Surveyor Topography | 99
OUT-0099 | 2023-06-15 | Other | Sari | OPEX- 921438761454929636 | Withholding tax | Withholding Tax | Withholding tax | Common | -100000 | 15000 | -6.6667 | 2023-06-01 | Manual | Unflagged | Pph 23 Kalindo 2.0- Additional setting out for Subdivision palm E2, E3, Horizon Ridge Top & Canopy House Surveyor Topography (2.5% x IDR 4.000.000) | 100
OUT-0100 | 2023-06-20 23:59 | Kalindo 2.0 | Cash Movements | XW7072949658981 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 30000 | 15000 | 2 | 2023-06-01 | Matched | Unflagged | MONTHLY ADMIN FEE | 101
OUT-0101 | 2023-06-20 23:59 | Kalindo 2.0 | Cash Movements | BG1610125476569 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 75000 | 15000 | 5 | 2023-06-01 | Matched | Unflagged | MONTHLY ADMIN FEE | 102
OUT-0102 | 2023-06-23 08:30 | Kalindo 2.0 | Cash Movements | 369214DI58987256 | Nusantara Studio | Architect Cost | Architect Cost | Common | 2900 | 15000 | 0.19333 | 2023-06-01 | Matched | Budgeted | Nusantara Studio 5:PR065403/JUN2023 BANK ARTHA 46 PT Nusantara Studio 5 05892527 769612167070949412 | 103
OUT-0103 | 2023-06-23 08:30 | Kalindo 2.0 | Cash Movements | 369214DI58987256 | Nusantara Studio | Architect Cost | Architect Cost | Common | 939101129 | 15000 | 62606.7419 | 2023-06-01 | Matched | Budgeted | Nusantara Studio 5:PR065403/JUN2023 BANK ARTHA 46 PT Nusantara Studio 5 05892527 769612167070949412 | 104
OUT-0104 | 2023-06-27 13:43 | Kalindo 2.0 | Cash Movements | 965296J456525856 | SDK Interiors | Marketing & Sales | Interior Designer | Common | 399750 | 15000 | 26.65 | 2023-06-01 | Matched | Budgeted | RM No: 2361670541456907496 SD Meridian INV 1161 ARCHITECTUREFEE 48 Elm Court Lane ET67ARKB07214905274543 | 105
OUT-0105 | 2023-06-27 13:43 | Kalindo 2.0 | Cash Movements | 965296J456525856 | SDK Interiors | Marketing & Sales | Interior Designer | Common | 75000 | 15000 | 5 | 2023-06-01 | Matched | Budgeted | RM No: 2361670541456907496 SD Meridian INV 1161 ARCHITECTUREFEE 48 Elm Court Lane ET67ARKB07214905274543 | 106
OUT-0106 | 2023-06-27 13:43 | Kalindo 2.0 | Cash Movements | 965296J456525856 | SDK Interiors | Marketing & Sales | Interior Designer | Common | 214821900 | 15000 | 14321.46 | 2023-06-01 | Matched | Budgeted | RM No: 2361670541456907496 SD Meridian INV 1161 ARCHITECTUREFEE 48 Elm Court Lane ET67ARKB07214905274543 | 107
OUT-0107 | 2023-06-30 23:59 | Kalindo 2.0 | Cash Movements | BG1232547056769 | Withholding tax | Withholding tax | Withholding tax | Common | 3947.15 | 15000 | 0.26314 | 2023-06-01 | Matched | Unflagged | WITHHOLDING TAX | 108
OUT-0108 | 2023-06-30 23:59 | Kalindo 2.0 | Cash Movements | WF8589430103694 | Withholding tax | Withholding tax | Withholding tax | Common | 123000 | 15000 | 8.2 | 2023-06-01 | Matched | Unflagged | WITHHOLDING TAX | 109
OUT-0109 | 2023-07-01 | Internal Allocation | Internal Allocation |  | Kalindo Resort A&G allocation | A&G Allocation | A&G Allocation | Common | 412500000 | 15000 | 27500 | 2023-07-01 | Manual | Unflagged | Jul 2023 A&G Allocation | 110
OUT-0110 | 2023-07-06 | OPEX IDR-060723 | Sari's recon | OPEX IDR-060723 | Meridian Tax Advisors | Tax & legal advice | Tax & legal advice | Common | 6000000 | 15000 | 400 | 2023-07-01 | Manual | Budgeted | Kalindo 2.0-Meridian:Inv 015/06/2023 - 40% Balance drafting reserva | 111
OUT-0111 | 2023-07-06 | OPEX IDR-060723 | Sari's recon | OPEX IDR-060723 | Meridian Tax Advisors | Tax & legal advice | Tax & legal advice | Common | 125701654 | 15000 | 8380.1103 | 2023-07-01 | Manual | Budgeted | Kalindo 2.0-Meridian:Inv 015/06/2023 - Assistance with the developm | 112
OUT-0112 | 2023-07-14 08:18 | Kalindo 2.0 | Cash Movements | 274709CR41250527 | BTR | Quantity Surveyor | Quantity Surveyor | Common | 2900 | 15000 | 0.19333 | 2023-07-01 | Matched | Unflagged | BTR: Ref.Sub/23067/GC/VI/2023 PT BANK MERIDIAN INDONE PT Bintang Trirasa 909030129654 509632703214749656 | 113
OUT-0113 | 2023-07-14 08:18 | Kalindo 2.0 | Cash Movements | 274709CR41250527 | BTR | Quantity Surveyor | Quantity Surveyor | Common | 142138865 | 15000 | 9475.9243 | 2023-07-01 | Matched | Budgeted | BTR: Ref.Sub/23067/GC/VI/2023 PT BANK MERIDIAN INDONE PT Bintang Trirasa 909030129654 509632703214749656 | 114
OUT-0114 | 2023-07-14 08:18 | Kalindo 2.0 | Cash Movements | 787276ZA10981018 | BTR | Quantity Surveyor | Quantity Surveyor | Common | 2900 | 15000 | 0.19333 | 2023-07-01 | Matched | Unflagged | BTR: Ref.Sub/2306/GC/III/2023 PT BANK MERIDIAN INDONE PT Bintang Trirasa 909030129654 072969416141612381 | 115
OUT-0115 | 2023-07-14 08:18 | Kalindo 2.0 | Cash Movements | 787276ZA10981018 | BTR | Quantity Surveyor | Quantity Surveyor | Common | 48375000 | 15000 | 3225 | 2023-07-01 | Matched | Budgeted | BTR: Ref.Sub/2306/GC/III/2023 PT BANK MERIDIAN INDONE PT Bintang Trirasa 909030129654 072969416141612381 | 116
OUT-0116 | 2023-07-20 23:59 | Kalindo 2.0 | Cash Movements | IZ2901418767878 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 30000 | 15000 | 2 | 2023-07-01 | Matched | Unflagged | MONTHLY ADMIN FEE | 117
OUT-0117 | 2023-07-20 23:59 | Kalindo 2.0 | Cash Movements | CZ6725832381612 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 75000 | 15000 | 5 | 2023-07-01 | Matched | Unflagged | MONTHLY ADMIN FEE | 118
OUT-0118 | 2023-07-31 | Internal Recon | Internal Recon |  | OFFICIAL Partners New Development | Other professional fees | Other professional fees | Common | 600000000 | 15000 | 40000 | 2023-07-01 | Manual | Unflagged | OFFICIAL Partners New Development fees | 119
OUT-0119 | 2023-07-31 11:14 | Kalindo 2.0 | Cash Movements | 030963UD01214763 | Nusantara Studio | Architect Cost | Architect Cost | Common | 2900 | 15000 | 0.19333 | 2023-07-01 | Matched | Budgeted | Nusantara Studio 5: DP Architectural Kiri Amahu 3 BANK ARTHA 46 PT Nusantara Studio 5 05892527 474121690527034187 | 120
OUT-0120 | 2023-07-31 11:14 | Kalindo 2.0 | Cash Movements | 030963UD01214763 | Nusantara Studio | Architect Cost | Architect Cost | Common | 159746395 | 15000 | 10649.7597 | 2023-07-01 | Matched | Budgeted | Nusantara Studio 5: DP Architectural Kiri Amahu 3 BANK ARTHA 46 PT Nusantara Studio 5 05892527 474121690527034187 | 121
OUT-0121 | 2023-07-31 23:59 | Kalindo 2.0 | Cash Movements | TA7292109410165 | Withholding tax | Withholding Tax | Withholding tax | Common | 5603.78 | 15000 | 0.37359 | 2023-07-01 | Matched | Unflagged | WITHHOLDING TAX | 122
OUT-0122 | 2023-07-31 23:59 | Kalindo 2.0 | Cash Movements | NK7092121418705 | Withholding tax | Withholding Tax | Withholding tax | Common | 100950 | 15000 | 6.73 | 2023-07-01 | Matched | Unflagged | WITHHOLDING TAX | 123
OUT-0123 | 2023-08-01 | Internal Allocation | Internal Allocation |  | Kalindo Resort A&G allocation | A&G Allocation | A&G Allocation | Common | 412500000 | 15000 | 27500 | 2023-08-01 | Manual | Unflagged | Aug 2023 A&G Allocation | 124
OUT-0124 | 2023-08-11 08:15 | Kalindo 2.0 | Cash Movements | 109410ZO90921436 | Java PM | Project Management | Project Management | Common | 2900 | 15000 | 0.19333 | 2023-08-01 | Matched | Unflagged | Java PM: Kalindo 2.0- Room Rental 1mo BMA (BANK MITRA A Ayu Kartika Le 8743412121 125616761056925210 | 125
OUT-0125 | 2023-08-11 08:15 | Kalindo 2.0 | Cash Movements | 109410ZO90921436 | Java PM | Project Management | Project Management | Common | 2900000 | 15000 | 193.3333 | 2023-08-01 | Matched | Budgeted | Java PM: Kalindo 2.0- Room Rental 1mo BMA (BANK MITRA A Ayu Kartika Le 8743412121 125616761056925210 | 126
OUT-0126 | 2023-08-18 14:53 | Kalindo 2.0 | Cash Movements | 561412LI56523296 | PPAT Wulandari | Notary | Notary | Common | 2900 | 15000 | 0.19333 | 2023-08-01 | Matched | Unflagged | Notary Wulandari: alindo 2.0- HGB Split BANK SEJAHTERA INDONES Wulandari Kusuma Sa 018727252361234 345210343092389690 | 127
OUT-0127 | 2023-08-18 14:53 | Kalindo 2.0 | Cash Movements | 561412LI56523296 | PPAT Wulandari | Notary | Notary | Common | 335000000 | 15000 | 22333.3333 | 2023-08-01 | Matched | Budgeted | Notary Wulandari: alindo 2.0- HGB Split BANK SEJAHTERA INDONES Wulandari Kusuma Sa 018727252361234 345210343092389690 | 128
OUT-0128 | 2023-08-20 23:59 | Kalindo 2.0 | Cash Movements | ED4383418541816 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 30000 | 15000 | 2 | 2023-08-01 | Matched | Unflagged | MONTHLY ADMIN FEE | 129
OUT-0129 | 2023-08-20 23:59 | Kalindo 2.0 | Cash Movements | HU3614909092385 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 75000 | 15000 | 5 | 2023-08-01 | Matched | Unflagged | MONTHLY ADMIN FEE | 130
OUT-0130 | 2023-08-31 23:59 | Kalindo 2.0 | Cash Movements | OH0163630561878 | Withholding tax | Withholding Tax | Withholding tax | Common | 1193.27 | 15000 | 0.079551 | 2023-08-01 | Matched | Unflagged | WITHHOLDING TAX | 131
OUT-0131 | 2023-08-31 23:59 | Kalindo 2.0 | Cash Movements | QV0921296387634 | Withholding tax | Withholding Tax | Withholding tax | Common | 93750 | 15000 | 6.25 | 2023-08-01 | Matched | Unflagged | WITHHOLDING TAX | 132
OUT-0132 | 2023-09-01 | Internal Allocation | Internal Allocation |  | Kalindo Resort A&G allocation | A&G Allocation | A&G Allocation | Common | 412500000 | 15000 | 27500 | 2023-09-01 | Manual | Unflagged | Sep 2023 A&G Allocation | 133
OUT-0133 | 2023-09-20 23:59 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | Cash Movements | GD6521072123652 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 30000 | 15000 | 2 | 2023-09-01 | Matched | Unflagged |  | 134
OUT-0134 | 2023-09-20 23:59 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | Cash Movements | QD8367672121830 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 75000 | 15000 | 5 | 2023-09-01 | Matched | Unflagged |  | 135
OUT-0135 | 2023-09-21 08:14 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | Cash Movements | 694127GP81832985 | Clearpoint Legal Solutions | Tax & legal advice | Tax & legal advice | Common | 2900 | 15000 | 0.19333 | 2023-09-01 | Matched | Unflagged |  | 136
OUT-0136 | 2023-09-21 08:14 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | Cash Movements | 694127GP81832985 | Clearpoint Legal Solutions | Tax & legal advice | Tax & legal advice | Common | 53183553 | 15000 | 3545.5702 | 2023-09-01 | Matched | Unflagged |  | 137
OUT-0137 | 2023-09-30 23:59 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | Cash Movements | ZW9278945812383 | Withholding tax | Withholding Tax | Withholding tax | Common | 86700 | 15000 | 5.78 | 2023-09-01 | Matched | Unflagged |  | 138
OUT-0138 | 2023-10-01 | Internal Allocation | Internal Allocation |  | Kalindo Resort A&G allocation | A&G Allocation | A&G Allocation | Common | 412500000 | 15000 | 27500 | 2023-10-01 | Manual | Unflagged | Oct 2023 A&G Allocation | 139
OUT-0139 | 2023-10-03 08:10 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | Cash Movements | 832561OD41050587 | CV. Ardana Solusi Engineering | MEP Consultant | MEP Consultant | Common | 2900 | 15000 | 0.19333 | 2023-10-01 | Matched | Unflagged | Ardana Solusi: Kalindo 2.0- Inv 183/HSE/IX BANK ARTHA 46 CV. Ardana Solusi 5694967494 121690107836769830 | 140
OUT-0140 | 2023-10-03 08:10 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | Cash Movements | 832561OD41050587 | CV. Ardana Solusi Engineering | MEP Consultant | MEP Consultant | Common | 3225000 | 15000 | 215 | 2023-10-01 | Matched | Budgeted | Ardana Solusi: Kalindo 2.0- Inv 183/HSE/IX BANK ARTHA 46 CV. Ardana Solusi 5694967494 121690107836769830 | 141
OUT-0141 | 2023-10-16 08:12 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | Cash Movements | 634921GR87230769 | CV. Ardana Solusi Engineering | MEP Consultant | MEP Consultant | Common | 2900 | 15000 | 0.19333 | 2023-10-01 | Matched | Unflagged | Ardana Solusi Eng:Inv187188 BANK ARTHA 46 CV. Ardana Solusi 5694967494 632705896547616501 | 142
OUT-0142 | 2023-10-16 08:12 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | Cash Movements | 634921GR87230769 | CV. Ardana Solusi Engineering | MEP Consultant | MEP Consultant | Common | 72508750 | 15000 | 4833.9167 | 2023-10-01 | Matched | Budgeted | Ardana Solusi Eng:Inv187188 BANK ARTHA 46 CV. Ardana Solusi 5694967494 632705896547616501 | 143
OUT-0143 | 2023-10-20 23:59 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | Cash Movements | XI1472707818165 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 75000 | 15000 | 5 | 2023-10-01 | Matched | Unflagged | MONTHLY ADMIN FEE | 144
OUT-0144 | 2023-10-20 23:59 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | Cash Movements | JE7092983416185 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 30000 | 15000 | 2 | 2023-10-01 | Matched | Unflagged | MONTHLY ADMIN FEE | 145
OUT-0145 | 2023-10-30 12:34 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | Cash Movements | 3292725878367016 | SDK Interiors | Marketing & Sales | Interior Designer | Common | 379800 | 15000 | 25.32 | 2023-10-01 | Matched | Budgeted | RM No: 0743872705294321210 SD Meridian INV 1182 1161 48 Elm Court Lane ET67ARKB07214905274543 | 146
OUT-0146 | 2023-10-30 12:34 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | Cash Movements | 3292725878367016 | SDK Interiors | Marketing & Sales | Interior Designer | Common | 75000 | 15000 | 5 | 2023-10-01 | Matched | Budgeted | RM No: 0743872705294321210 SD Meridian INV 1182 1161 48 Elm Court Lane ET67ARKB07214905274543 | 147
OUT-0147 | 2023-10-30 12:34 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | Cash Movements | 3292725878367016 | SDK Interiors | Marketing & Sales | Interior Designer | Common | 47333100 | 15000 | 3155.54 | 2023-10-01 | Matched | Budgeted | RM No: 0743872705294321210 SD Meridian INV 1182 1161 48 Elm Court Lane ET67ARKB07214905274543 | 148
OUT-0148 | 2023-10-31 23:59 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | Cash Movements | ST8521676709036 | Withholding tax | Withholding Tax | Withholding tax | Common | 578.93 | 15000 | 0.038595 | 2023-10-01 | Matched | Unflagged | WITHHOLDING TAX | 149
OUT-0149 | 2023-10-31 23:59 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | Cash Movements | PA9018101056181 | Withholding tax | Withholding Tax | Withholding tax | Common | 5.81 | 15000 | 0.00038733 | 2023-10-01 | Matched | Unflagged | WITHHOLDING TAX | 150
OUT-0150 | 2023-11-01 | Internal Allocation | Internal Allocation |  | Kalindo Resort A&G allocation | A&G Allocation | A&G Allocation | Common | 412500000 | 15000 | 27500 | 2023-11-01 | Manual | Unflagged | Nov 2023 A&G Allocation | 151
OUT-0151 | 2023-11-17 08:11 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | Cash Movements | 216709MX27276367 | BTR | Quantity Surveyor | Quantity Surveyor | Common | 2900 | 15000 | 0.19333 | 2023-11-01 | Matched | Unflagged | BTR: Inv 2 IN202300322 PT BANK MERIDIAN INDONE PT Bintang Trirasa 909030129654 163450905072947896 | 152
OUT-0152 | 2023-11-17 08:11 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | Cash Movements | 216709MX27276367 | BTR | Quantity Surveyor | Quantity Surveyor | Common | 31950000 | 15000 | 2130 | 2023-11-01 | Matched | Unflagged | BTR: Inv 2 IN202300322 PT BANK MERIDIAN INDONE PT Bintang Trirasa 909030129654 163450905072947896 | 153
OUT-0153 | 2023-11-20 08:09 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | Cash Movements | 654389YB83072989 | BTR | Quantity Surveyor | Quantity Surveyor | Common | 2900 | 15000 | 0.19333 | 2023-11-01 | Matched | Unflagged | BTR: Inv 2 IN202300322 BP PT BANK MERIDIAN INDONE PT Bintang Trirasa 909030129654 345858909452745652 | 154
OUT-0154 | 2023-11-20 08:09 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | Cash Movements | 654389YB83072989 | BTR | Quantity Surveyor | Quantity Surveyor | Common | 300000 | 15000 | 20 | 2023-11-01 | Matched | Unflagged | BTR: Inv 2 IN202300322 BP PT BANK MERIDIAN INDONE PT Bintang Trirasa 909030129654 345858909452745652 | 155
OUT-0155 | 2023-11-20 23:59 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | Cash Movements | AT2943036107250 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 30000 | 15000 | 2 | 2023-11-01 | Matched | Unflagged | MONTHLY ADMIN FEE | 156
OUT-0156 | 2023-11-20 23:59 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | Cash Movements | JW9290989456127 | Bank Monthly Fees | Miscellaneous | Miscellaneous | Common | 75000 | 15000 | 5 | 2023-11-01 | Matched | Unflagged | MONTHLY ADMIN FEE | 157
OUT-0157 | 2023-12-01 | Internal Allocation | Internal Allocation |  | Kalindo Resort A&G allocation | A&G Allocation | A&G Allocation | Common | 412500000 | 15000 | 27500 | 2023-12-01 | Manual | Unflagged | Dec 2023 A&G Allocation | 158
Formulas:
Period = DATE(YEAR([Date]),MONTH([Date]),1)

## Inflows
Kalindo Cove - Inflow Ledger
Transaction-level sales receipts and account income translated at monthly average FX and reconciled to bank references.
Actual receipts through cut-off
| 832913.0924 | Sales receipts | 832531.8 | Unmatched bank rows | 0 | [7 empty] | ← Back to Cover
Txn ID | Date | Bank / Account | Reference No | Income Source | Original Type | Standard Unit / Type | Amount IDR | FX IDR / USD | Amount USD | Period | Bank Status | Budgeted Income USD | Variance USD | Description / Note | Source Row
INF-0001 | 2022-12-31 23:59 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | JE5658549038347 | IDR Account | Credit Interest | Other income | 1862.33 | 15731 | 0.11839 | 2022-12-01 | Matched | 0 | 0 | CREDIT INTEREST | 2
INF-0002 | 2023-06-30 23:59 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | ST2721036749854 | IDR Account | Credit Interest | Other income | 19735.76 | 15000 | 1.3157 | 2023-06-01 | Matched | 0 | 0 | CREDIT INTEREST | 3
INF-0003 | 2023-07-31 23:59 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | EV8789036161834 | IDR Account | Credit Interest | Other income | 28018.9 | 15000 | 1.8679 | 2023-07-01 | Matched | 0 | 0 | CREDIT INTEREST | 4
INF-0004 | 2023-08-31 23:59 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | ZK9496565450921 | IDR Account | Credit Interest | Other income | 5966.36 | 15000 | 0.39776 | 2023-08-01 | Matched | 0 | 0 | CREDIT INTEREST | 5
INF-0005 | 2023-10-31 23:59 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | DG7232963218529 | IDR Account | Credit Interest | Other income | 2894.67 | 15000 | 0.19298 | 2023-10-01 | Matched | 0 | 0 | CREDIT INTEREST | 6
INF-0006 | 2022-12-29 13:11 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 234907AV87236149 | Payment Thomas Whitfield | Horizon Ridge Top | Horizon Ridge Top | 3492203345 | 15731 | 221995 | 2022-12-01 | Matched | 2800000 | -2578005 | BizChannel TRF FR KALINDO ADVENTURE Payment from Thomas Whitfield | 7
INF-0007 | 2022-12-31 23:59 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | YV6327672963098 | USD Account | Credit Interest | Other income | 28158.49 | 15731 | 1.79 | 2022-12-01 | Matched | 0 | 0 | CREDIT INTEREST | 8
INF-0008 | 2023-01-31 23:59 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | KB2381458963696 | USD Account | Credit Interest | Other income | 301077.9 | 14979 | 20.1 | 2023-01-01 | Matched | 0 | 0 | CREDIT INTEREST | 9
INF-0009 | 2023-02-16 08:02 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 212945YFKP610769 | Payment Thomas Whitfield | Horizon Ridge Top | Horizon Ridge Top | 3390751630 | 15274 | 221995 | 2023-02-01 | Matched | 2800000 | -2578005 | INCOMING SWIFT 4767278983470105 THOMAS BRADLEY WHITFIELD TTEE INV 001/KAS/KALINDO 2.0/0223 | 10
INF-0010 | 2023-02-28 23:59 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | UH4723036709274 | USD Account | Credit Interest | Other income | 443862.44 | 15274 | 29.06 | 2023-02-01 | Matched | 0 | 0 | CREDIT INTEREST | 11
INF-0011 | 2023-03-31 23:59 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | RO9852169296369 | USD Account | Credit Interest | Other income | 702943.54 | 15062 | 46.67 | 2023-03-01 | Matched | 0 | 0 | CREDIT INTEREST | 12
INF-0012 | 2023-04-30 23:59 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | LU5634981056961 | USD Account | Credit Interest | Other income | 665250 | 15000 | 44.35 | 2023-04-01 | Matched | 0 | 0 | CREDIT INTEREST | 13
INF-0013 | 2023-05-31 23:59 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | OR4101096561892 | USD Account | Credit Interest | Other income | 685200 | 15000 | 45.68 | 2023-05-01 | Matched | 0 | 0 | CREDIT INTEREST | 14
INF-0014 | 2023-06-30 23:59 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | AJ2107296525634 | USD Account | Credit Interest | Other income | 615300 | 15000 | 41.02 | 2023-06-01 | Matched | 0 | 0 | CREDIT INTEREST | 15
INF-0015 | 2023-07-31 23:59 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | HO9674709096129 | USD Account | Credit Interest | Other income | 504450 | 15000 | 33.63 | 2023-07-01 | Matched | 0 | 0 | CREDIT INTEREST | 16
INF-0016 | 2023-08-31 23:59 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | HW5672347252941 | USD Account | Credit Interest | Other income | 468750 | 15000 | 31.25 | 2023-08-01 | Matched | 0 | 0 | CREDIT INTEREST | 17
INF-0017 | 2023-09-30 23:59 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | YF0543896941258 | USD Account | Credit Interest | Other income | 433350 | 15000 | 28.89 | 2023-09-01 | Matched | 0 | 0 | CREDIT INTEREST | 18
INF-0018 | 2023-10-31 23:59 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | LO1812527870763 | USD Account | Credit Interest | Other income | 435750 | 15000 | 29.05 | 2023-10-01 | Matched | 0 | 0 | CREDIT INTEREST | 19
INF-0019 | 2023-11-21 08:08 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 189836XIVE785250 | Payment Julien | Meadow 1 | Meadow 1 | 2340007500 | 15000 | 156000.5 | 2023-11-01 | Matched | 800000 | -643999.5 | INCOMING SWIFT K3210305 767 9 ISABELLA MARIE CONTI PAID AS SHAREHOLDER OF PT CONTI PRIMA | 20
INF-0020 | 2023-11-22 11:28 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 143652NQXG385870 | Payment Julien | Meadow 1 | Meadow 1 | 2324992500 | 15000 | 154999.5 | 2023-11-01 | Matched | 800000 | -645000.5 | INCOMING SWIFT 4385630501672549 KADEK LARASATI DEWI S.HM.KN. /INV/DP PEMBELIAN TANAH | 21
INF-0021 | 2023-11-30 23:59 | Account : 254323078101/KALINDO ADVENTURE SPORTS(IDR) | IJ2785694163896 | IDR Account | Credit Interest | Other income | 4944.49 | 15000 | 0.32963 | 2023-11-01 | Pending feed | 0 | 0 | CREDIT INTEREST | 22
INF-0022 | 2023-11-27 08:12 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | 476909YBUZ494581 | Payment Julien | Meadow 1 | Meadow 1 | 1163127000 | 15000 | 77541.8 | 2023-11-01 | Pending feed | 800000 | -722458.2 | INCOMING SWIFT 9678769892TW ISABELLA MARIE CONTI 52 GLENTWOR /ROC/9678769892TW///URI/PAID AS SHA | 23
INF-0023 | 2023-11-30 23:59 | Account : 812741832741/KALINDO ADVENTURE SPORTS(USD) | YP0149430923010 | USD Account | Credit Interest | Other income | 383700 | 15000 | 25.58 | 2023-11-01 | Pending feed | 0 | 0 | CREDIT INTEREST | 24
Formulas:
Period = DATE(YEAR([Date]),MONTH([Date]),1)

## Checks (hidden)
Kalindo Cove - Model Checks | [7 empty] | ← Back to Cover
One assertion per row. PASS means the workbook reconciles within the stated tolerance.
MODEL STATUS | [8 empty] | ← Back to Cover
Check Summary | [5 empty] | PASS
ID | Check | Actual | Expected | Difference | Tolerance | Status | Where to fix / Notes
CHK01 | Villa buildup factors sum to 100% | 1 | 1 | 0 | 0.0001 | PASS | Villas P6:P14
CHK02 | Villa land factors sum to 100% | 1 | 1 | 0 | 0.0001 | PASS | Villas Q6:Q14
CHK03 | Budget allocation ties | 0 | 0 | 0 | 1 | PASS | Allocation budget block
CHK04 | Actual allocation ties | 0 | 0 | 0 | 1 | PASS | Allocation actual block
CHK05 | EAC allocation ties | 0 | 0 | 0 | 1 | PASS | Allocation EAC block
CHK06 | Unit P&L EAC equals allocated P&L costs | 10250864.5744 | 10250864.5744 | 0 | 1 | PASS | Unit P&L / Budget
CHK07 | Sales receipt plans reconcile | 0 | 0 | 0 | 1 | PASS | Sales Plan receipt control
CHK08 | Cash Flow actual inflows tie to ledger | 832913.0924 | 832913.0924 | 0 | 1 | PASS | Cash Flow actual inflows
CHK09 | Cash Flow actual outflows tie to ledger | 788238.5499 | 788238.5499 | 0 | 1 | PASS | Cash Flow actual outflows
CHK10 | Outflows mapped to standard categories | 0 | 0 | 0 | 0 | PASS | Inputs category mapping
CHK11 | Bank-sourced outflows matched | 0 | 0 | 0 | 0 | PASS | Outflows bank status
CHK12 | Inflows matched to bank feeds | 0 | 0 | 0 | 0 | PASS | Inflows bank status
CHK13 | IDR bank feed movement ties | 7.4506e-08 | 0 | 7.4506e-08 | 1 | PASS | Bank_IDR summary; source may be unsorted within a day
CHK14 | USD bank feed movement ties | 0 | 0 | 0 | 1 | PASS | Bank_USD summary; source may be unsorted within a day
CHK15 | Cash roll-forward identity | 0 | 0 | 0 | 1 | PASS | Cash Flow final month
CHK16 | No negative forecast months | 0 | 0 | 0 | 0 | PASS | Budget schedule
CHK17 | P&L revenue ties to Villas | 12067713.0537 | 12067713.0537 | 0 | 1 | PASS | Unit P&L / Villas